## PISC1132S Land Acquisition All
Land Acquisition, All Acquisition Data for BPA's Fish & Wildlife Program
(As of 03/27/2019)
Work Element / Parcel | [6 empty] | Project Information | [5 empty] | Land Acquisition Details | [6 empty] | Land Acquisition Process Steps | [5 empty] | Metrics
Sponsor | Work Element Title (Parcel Name) | Tract ID | State (GIS Determined) | Subbasin (GIS Determined) | County (GIS Determined) | Time Frame | WEStatus | Project # | Project Title | Expense or Capital | BPA PM | BPA Land PM | Total Number of Acres Protected (Metric) | Type of Acquisition (Metric) | Lat Long | Planned Budget Amt | Estimated Acq. Cost (BPA portion only) (WE Budget) | Fiscal Year | Completed Acquisition (DELIV) | Appraisal Submitted Date (ASD) | Appraisal Approved Date )(AAD) | Purchase And Sale Agreement Date (PSA) | 945 Review Date (945) | Public Notice Date (PN) | Authorization To Spend Funds Date (ATSF) | Start Latitude Of Protected Stream Reach Planned Value | Start Latitude Of Protected Stream Reach Actual Value | End Latitude Of Protected Stream Reach Planned Value | End Latitude Of Protected Stream Reach Actual Value | Start Longitude Of Protected Stream Reach Planned Value | Start Longitude Of Protected Stream Reach Actual Value | End Longitude Of Protected Stream Reach Planned Value | End Longitude Of Protected Stream Reach Actual Value | Number Of Acres Of Upland Non Wetland Habitat Protected Planned Value | Number Of Acres Of Upland Non Wetland Habitat Protected Actual Value | Number Of Acres Of Upland Wetland Habitat Protected Planned Value | Number Of Acres Of Upland Wetland Habitat Protected Actual Value | Number Of Acres Of Riparian Non Wetland Habitat Protected Planned Value | Number Of Acres Of Riparian Non Wetland Habitat Protected Actual Value | Number Of Acres Of Riparian Wetland Habitat Protected Planned Value | Number Of Acres Of Riparian Wetland Habitat Protected Actual Value | Number Of Acres Of Freshwater Non Wetland Habitat Protected Planned Value | Number Of Acres Of Freshwater Non Wetland Habitat Protected Actual Value | Number Of Acres Of Freshwater Wetland Habitat Protected Planned Value | Number Of Acres Of Freshwater Wetland Habitat Protected Actual Value | Number Of Acres Of Estuarine Wetland Habitat Protected Planned Value | Number Of Acres Of Estuarine Wetland Habitat Protected Actual Value | Number Of Acres Of Estuarine Non Wetland Habitat Protected Planned Value | Number Of Acres Of Estuarine Non Wetland Habitat Protected Actual Value | Number Of Miles Protected Ina Riparian Wetland Area Planned Value | Number Of Miles Protected Ina Riparian Wetland Area Actual Value | Number Of Miles Protected Ina Riparian Non Wetland Area Planned Value | Number Of Miles Protected Ina Riparian Non Wetland Area Actual Value
Yakama Confederated Tribes | Tribal Data
Colville Confederated Tribes
Oregon Department of Fish and Wildlife
Yakama Confederated Tribes
Colville Confederated Tribes
Colville Confederated Tribes
Colville Confederated Tribes
Nature Conservancy | BASKET BUTTE | WILMIT-WL-13 | OR | Willamette | Polk |  | COMPLETED | 2009-017-00 | TNC Willamette Wildlife Acquisitions | Cap | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 | 480000 | 482269 | 2010 | 2009-11-13 | 2009-11-13 | 2009-11-13 | 2009-11-13 | 2009-11-13 | 2009-11-13 | 2009-11-13 | [8 empty] | 155.00 | 155.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Big Meadows-Flesher/PRIEST RIVER (KT) | ALFD-WL-46 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 | 480000 | 476013 | 2010 | 2010-09-27 | 2010-08-30 | 2010-08-30 | 2010-09-22 | 2010-06-28 | 2010-05-27 | 2010-03-26 | [8 empty] | 3.00 | 3.00 | 140.00 | 140.00 | 0.00 | 0.00 | 10.00 | 10.00 | 0.00 | 0.00 | 150.00 | 150.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
Yakama Confederated Tribes | Tribal Data | [51 empty] | 0.50
Oregon Department of Fish and Wildlife | BUENA VISTA (GLT) | WILMIT-WL-5 | OR | Willamette | Polk |  |  | 1992-068-00 | Willamette Basin Mitigation | Cap | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 |  | 486824 | 2009 | 2009-09-29 | 2009-09-15 | 2009-09-15 | 2009-09-15 | 2009-09-15 | 2009-09-15 | 2009-09-15
Colville Confederated Tribes | Tribal Data | SLMN-CK-WL-1 | WA | Okanogan | Okanogan |  |  |  | Land & Water Acquisition
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Clark Fork River Delta-WHITE ISLAND (IDFG) | ALFD-WL-39 | ID | Clark Fork | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 | 1300000 | 1225852 | 2010 | 2010-09-27 | 2010-08-31 | 2010-08-31 | 2010-09-14 | 2010-07-29 | 2010-06-30 | 2009-10-01 | [8 empty] | 0.00 | 0.00 | 30.00 | 30.00 | 60.00 | 60.00 | 41.00 | 41.00 | 0.00 | 0.00 | 131.00 | 131.00 | 0.00 | 0.00 | 0.00 | 0.00 | 1.00 | 1.00 | 0.00 | 0.00
Umatilla Confederated Tribes (CTUIR) | Tribal Data
Idaho Department of Fish and Game (IDFG) | Hammer Flat (IDFG) | SIDHO-WL-18 | ID | Boise | Ada |  |  | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , |  | New Easement | 44.5129, -114.173 | 4230000 | 4237490 | 2012 | 2012-06-27 |  |  | 2011-12-12 | 2011-12-06 | [10 empty] | 705.00 | 705.00 | [16 empty] | 0.00
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Hayden Lake--TALL PINES (IDFG) | ALFD-WL-48 | ID | Spokane | Kootenai |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 | 1750665 | 1750665 | 2011 | 2011-02-02 | 2011-02-02 | 2011-02-02 | 2011-01-25 | 2010-12-02 | 2010-11-03 | 2010-10-01 | [8 empty] | 203.00 | 203.00 | [16 empty] | 0.00 | 0.00
Salish and Kootenai Confederated Tribes | Tribal Data
Oregon Department of Fish and Wildlife | LITTLE WILLAMETTE (GLT) | WILMIT-WL-11 | OR | Willamette | Linn |  |  | 1992-068-00 | Willamette Basin Mitigation | Cap | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 | 700000 | 588034 | 2009 | 2009-09-29 | 2009-09-15 | 2009-09-15 | 2009-09-15 | 2009-09-15 | 2009-09-15 | 2009-09-15 | 44.619400 | 44.619400 | 44.623240 | 44.623240 | -123.164560 | -123.164560 | -123.164450 | -123.164450
Colville Confederated Tribes | Tribal Data
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Lower Pack River-Shields (IDFG) | ALFD-WL-40 | ID | Pend Oreille | Bonner |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 | 500000 | 1073208 | 2009 | 2009-09-28 |  |  | 2009-08-18 | 2009-09-01 | 2009-08-18 | 2009-01-30
Colville Confederated Tribes | Tribal Data
Colville Confederated Tribes
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | NIMZ RANCH (KToI) | ALFD-WL-38 | ID | Kootenai | Boundary |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 | 2230000 | 2238287 | 2009 | 2009-08-27 | 2008-10-01 | 2008-10-01 | 2009-06-08 | 2009-07-30 | 2009-07-30 | 2008-10-01
Colville Confederated Tribes | Tribal Data
Colville Confederated Tribes
Colville Confederated Tribes
Colville Confederated Tribes
Nez Perce Tribe
Colville Confederated Tribes
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | ROBINSON CREEK (CDA River Valley) IDFG | ALFD-WL-41 | ID | Coeur D'Alene | Kootenai |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 | 0 | 110419 | 2010 | 2009-11-05 | 2009-11-06 | 2009-11-06 | 2009-11-02 | [11 empty] | 15.00 | 15.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 15.00 | 15.00 | 34.00 | 34.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
Oregon Department of Fish and Wildlife | SOUTH EUGENE MEADOWS | WILMIT-WL-22 | OR | Willamette | Lane |  | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , |  | Fee Title | 44.5129, -114.173 | 886825 | 886825 | 2012 | 2011-12-02 | 2011-12-02 | 2011-12-02 | 2011-12-02 | 2011-12-02 | 2011-12-02 | 2011-12-02 | [8 empty] | 193.00 | 193.00 | [16 empty] | 0.00 | 0.00
Idaho Department of Fish and Game (IDFG) | Springfield Trout Hatchery (IDFG) | SPRNG-FSH-1 | ID | Snake Upper | Bingham |  | COMPLETED | 2007-402-00 | Snake River Sockeye Captive Propagation | Cap | Jonathan McCloud | , |  | Fee Title | 44.5129, -114.173 | 4750000 | 4750821 | 2010 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | [8 empty] | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Tacoma/Trimble-Kline (COCOLALLA LAKE) IDFG | NIDAHO-WL-1 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 | 0 | 300813 | 2010 | 2010-01-27 | 2010-02-12 | 2010-02-12 | 2010-02-12 | 2010-02-12 | 2010-02-12 | 2010-02-12 | [8 empty] | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 15.00 | 15.00 | 5.00 | 5.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.10 | 0.10 | 0.00 | 0.00
Oregon Department of Fish and Wildlife | TRAPPIST ABBEY | WILMIT-WL-16 | OR | Willamette | Yamhill |  | COMPLETED | 1992-068-00 | Willamette Basin Mitigation | Cap | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 | 9720000 | 9716071 | 2011 | 2010-10-27 |  |  | 2010-10-21 | [11 empty] | 1310.00 | 1310.00 | [16 empty] | 0.00 | 0.00
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Trimble Creek/R&T Community Trust/Doramus #2 (KT) | ALFD-WL-44 | WA | Pend Oreille | Pend Oreille |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 | 170000 | 173374 | 2010 | 2010-08-13 | 2010-08-17 | 2010-08-17 | 2010-07-14 | 2010-01-29 | 2009-10-01 | 2010-05-24 | [8 empty] | 6.00 | 6.00 | 66.00 | 66.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 66.00 | 66.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
Colville Confederated Tribes | Tribal Data
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Upper Twin Rivers/Moyie Springs (Kootenai) | ALFD-WL-51 | ID | Kootenai | Boundary |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 | 287000 | 270554 | 2012 | 2012-02-09 | 2012-02-10 | 2012-02-10 | 2012-02-10 | 2012-02-10 | 2012-02-10 | 2012-02-10
Colville Confederated Tribes | Tribal Data
US Fish and Wildlife Service (USFWS) | WAPATO LAKE UNIT 650 | TUALT-WL-2 | OR | Willamette | Yamhill |  |  | 2000-016-00 | Tualatin River National Wildlife Refuge Additions | Cap | Siena Lopez-Johnston | , |  | Fee Title | 44.5129, -114.173 | 90802 | 90802 | 2010 | 2010-05-17 | 2010-05-14 | 2010-05-14 | 2010-05-14 | 2010-05-14 | 2010-05-14 | 2010-05-14 | 45.426476 | 45.426476 | 45.436476 | 45.436476 | -123.135362 | -123.135362 | -123.224875 | -123.224875 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
US Fish and Wildlife Service (USFWS) | WAPATO LAKE UNIT 658 | TUALT-WL-1 | OR | Willamette | Yamhill |  |  | 2000-016-00 | Tualatin River National Wildlife Refuge Additions | Cap | Siena Lopez-Johnston | , |  | Fee Title | 44.5129, -114.173 | 502649 | 502549 | 2010 | 2010-04-16 | 2010-04-30 | 2010-04-30 | 2010-04-30 | 2010-04-30 | 2010-04-30 | 2010-04-30 | 45.425628 | 45.425628 | 45.410150 | 45.410150 | -123.165414 | -123.165414 | -123.116731 | -123.116731 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
US Fish and Wildlife Service (USFWS) | WAPATO LAKE UNIT 659 | TUALT-WL-4 | OR | Willamette | Washington |  |  | 2000-016-00 | Tualatin River National Wildlife Refuge Additions | Cap | Siena Lopez-Johnston | , |  | Fee Title | 44.5129, -114.173 | 101069 | 101069 | 2010 | 2010-05-17 | 2010-05-21 | 2010-05-21 | 2010-05-21 | 2010-05-21 | 2010-05-21 | 2010-05-21 | [8 empty] | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 28.26 | 28.26 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
US Fish and Wildlife Service (USFWS) | WAPATO LAKE UNIT 683 | TUALT-WL-3 | OR | Willamette | Washington |  |  | 2000-016-00 | Tualatin River National Wildlife Refuge Additions | Cap | Siena Lopez-Johnston | , |  | Fee Title | 44.5129, -114.173 | 311447 | 311447 | 2010 | 2010-05-17 | 2010-05-21 | 2010-05-21 | 2010-05-21 | 2010-05-21 | 2010-05-21 | 2010-05-21 | [8 empty] | 0.00 | 0.00 | 0.00 | 0.00 | 16.00 | 16.00 | 0.00 | 0.00 | 0.00 | 0.00 | 9.00 | 9.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
Nature Conservancy | Willamette Confluence Project - TNC | WILMIT-WL-10 | OR | Willamette | Lane |  | COMPLETED | 2009-017-00 | TNC Willamette Wildlife Acquisitions | Cap | Dorothy Welch | , |  | Fee Title | 44.5129, -114.173 | 20851010 | 20851010 | 2011 | 2010-10-27 | 2010-10-27 | 2010-10-27 | 2010-10-21 |  |  |  | 44.013200 | 44.013200 | 44.021500 | 44.021500 | -122.923800 | -122.923800 | -123.017100 | -123.017100 | [6 empty] | 415.00 | 415.00 | [8 empty] | 6.00 | 6.00
Nature Conservancy | WILLOW CREEK | WILMIT-WL-12 | OR | Willamette | Lane |  | COMPLETED | 2009-017-00 | TNC Willamette Wildlife Acquisitions | Cap | Dorothy Welch | , |  | Fee Title | 44.5129, -114.173 | 750000 | 754150 | 2010 | 2009-11-13 |  |  | 2009-10-10 |  | 2009-11-02 | [9 empty] | 10.45 | 10.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
Shoshone-Paiute Tribes | Tribal Data
National Fish and Wildlife Foundation | WITTE PLACE CONSERVATION EASEMENT (Pigott) | WENTY-WL-1 | WA | Methow | Okanogan |  | COMPLETED | 2002-013-01 | Water Entity - CBWTP | Exp | Maura Eagan Moody | , |  | New Easement | 44.5129, -114.173 | 570000 | 389000 | 2009 | 2009-09-15 | 2009-09-15 | 2009-09-15 | 2009-09-15 | 2009-09-15 | 2009-09-15 | 2009-09-15 |  | 48.378537 |  | 48.374128 |  | -120.118697 |  | -120.121682
Nature Conservancy | YAMHILL OAKS/MUDDY VALLEY | WILMIT-WL-19 | OR | Willamette | Yamhill |  | COMPLETED | 2009-017-00 | TNC Willamette Wildlife Acquisitions | Cap | Dorothy Welch | , |  | Fee Title | 44.5129, -114.173 | 500000 | 1008944 | 2010 | 2010-09-15 | 2010-09-15 | 2010-09-15 | 2010-09-15 | 2010-09-15 | 2010-09-15 | 2010-09-15 | 45.167700 | 45.167700 | 45.162200 | 45.162200 | -123.317600 | -123.317600 | -123.316700 | -123.316700 | 170.00 | 170.00 | 66.00 | 66.00 | 0.00 | 0.00 | 13.00 | 13.00 | 0.00 | 0.00 | 66.00 | 66.00 | 0.00 | 0.00 | 0.00 | 0.00 | 1.00 | 1.00 | 0.00 | 0.00
Columbia Land Trust | COLUMBIA STOCK RANCH (CSR) | COLSR-WL-1 | OR | Columbia Lower | Columbia |  | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , |  | New Easement | 44.5129, -114.173 | 5439000 | 5306043 | 2012 | 2012-01-20 | 2012-01-20 | 2012-01-20 | 2012-01-20 | 2012-01-20 | 2012-01-20 | 2012-01-20 | [22 empty] | 500.00 | 500.00 | 5.00 | 5.00
Idaho Department of Fish and Game (IDFG) | Payette River (Bicandi) IDFG | SIDHO-WL-17 | ID | Payette | Payette |  | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , |  | New Easement | 44.5129, -114.173 | 360000 | 360959 | 2012 | 2012-09-25
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | EATON LAKE/BEAVER SOUTH (South Eaton Lake) KT | ALFD-WL-19 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 70.0 | Mix | 44.5129, -114.173 |  | 1221503 | 2006 | 2006-01-11 |  |  |  | 2006-06-30 | 2005-11-18 | 2005-10-05
Oregon Department of Fish and Wildlife | Hall/Kings Valley/Luckiamute Meadows | WILWF-WL-13 | OR | Willamette | Benton | Q2 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 73.6 | New Easement | 44.5129, -114.173 | 562000 | 208082 | 2014 | 2014-04-11 | 2014-04-08 | 2013-08-16 | 2014-04-06 | 2013-10-01 | 2013-10-01 | 2013-10-01 | [8 empty] | 35.00 | 34.74 |  |  | 39.00 | 38.74
Umatilla Confederated Tribes (CTUIR) | Tribal Data
Salish and Kootenai Confederated Tribes
Spokane Tribe
Custer Soil and Water Conservation District (SWCD) | 12-Mile (Stark) Custer SWCD | TMPRJ-WL-1 |  |  |  | Q3 | COMPLETED | 1999-019-00 | Restore 12 Mile Reach of Upper Salmon River | Exp | Gerald McClintock | , |  | New Easement | 44.5129, -114.173 |  | 764616 | 2005 | 2005-06-07
Salish and Kootenai Confederated Tribes | Tribal Data
Colville Confederated Tribes
Yakama Confederated Tribes
Salish and Kootenai Confederated Tribes
Spokane Tribe
Spokane Tribe
Spokane Tribe
Spokane Tribe
Oregon Department of Fish and Wildlife | Andrew Reasoner Wildlife Preserve (Carnine/McKenzie) | WILWF-WL-31 | OR | Willamette | Lane | Q1 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 290.2 | New Easement | 44.5129, -114.173 | 269000 | 220492 | 2016 | 2015-12-21
Oregon Department of Fish and Wildlife | Atfalati Prairie-Phase #2 (Lozo) | WILWF-WL-34 | OR | Willamette | Washington | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 2.5 | New Easement | 44.5129, -114.173 | 12000 | 17690 | 2016 | 2016-09-28
Oregon Department of Fish and Wildlife | Atfalati Prairie-Schultz | WILWF-WL-27 | OR | Willamette | Washington | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 210.0 | New Easement | 44.5129, -114.173 | 1416360 | 1062972 | 2015 | 2015-08-25
Oregon Department of Fish and Wildlife | Austin Hot Springs | WILWF-WL-45 | OR | Willamette | Clackamas | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 151.7 | New Easement | 44.5129, -114.173 | 260000 | 280106 | 2017 | 2017-09-27
Lower Columbia Estuary Partnership | BAKERS BAY-Wallicut (CLT) | COLSR-WL-2 | WA | Columbia Estuary | Pacific |  | COMPLETED | 2003-011-00 | Columbia River Estuary Habitat Restoration | Exp | Anne Creason | , |  | New Easement | 44.5129, -114.173 | 573730 | 576730 | 2012 | 2012-01-19 | 2012-01-19 | 2012-01-19 | 2012-01-19 | 2012-01-19 | 2012-01-19 | 2012-01-19
Oregon Department of Fish and Wildlife | Bald Hill Property | WILWF-WL-7 | OR | Willamette | Benton | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 483.0 | New Easement | 44.5129, -114.173 | 1520000 | 1500000 | 2013 | 2013-07-09
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Beaver Lake 3 (Kalispel Accord) | ALFD-WL-70 | ID | Pend Oreille | Bonner | Q2 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 40.0 | New Easement | 44.5129, -114.173 | 203000 | 203432 | 2018 | 2018-02-26
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Beaver Lake North (Kornegut) KT | ALFD-WL-13 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 40.0 | Mix | 44.5129, -114.173 |  | 170203 | 2004 | 2004-09-14 |  |  |  | 2004-07-26 | 2004-06-24 | 2004-02-20
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | BEAVER LAKE NORTH-Bottle Bay (Hellar) KT | ALFD-WL-16 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 105.0 | Mix | 44.5129, -114.173 |  | 325837 | 2004 | 2004-09-24 |  |  |  | 2004-09-15 | 2004-08-04 | 2004-06-11
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | BEAVER LAKE-Bottle Bay (Strong) KT | ALFD-WL-5 | ID | Pend Oreille | Bonner | Q1 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Exp | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 |  | 850356 | 2003 | 2002-10-28
Coeur D'Alene Tribe | Tribal Data
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Oregon Department of Fish and Wildlife | BIG ISLAND ADDITION | WILMIT-WL-14 | OR | Willamette | Lane |  | COMPLETED | 1992-068-00 | Willamette Basin Mitigation | Exp | Dorothy Welch | , |  | Fee Title | 44.5129, -114.173 | 800000 | 0 | 2010 | 2009-12-04 | [20 empty] | 0.00 |  | 0.00 |  | 0.00 |  | 0.00 |  | 0.00 |  | 0.00
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | BIG MEADOWS (Jayo) KT | ALFD-WL-27 | ID | Pend Oreille | Bonner |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 |  | 2176506 | 2007 | 2007-05-01 | 2007-05-01 | 2007-05-01 | 2007-05-01 | 2006-11-02 | 2007-04-26 | 2007-05-01
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Big Meadows III/Priest Lake (Kalispel Accord) | ALFD-WL-58 | ID | Pend Oreille | Bonner | Q4 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 15.0 | New Easement | 44.5129, -114.173 | 85000 | 85216 | 2016 | 2016-09-21
Salish and Kootenai Confederated Tribes | Tribal Data
Shoshone-Paiute Tribes
Spokane Tribe
Salish and Kootenai Confederated Tribes
Shoshone-Bannock Tribes
Shoshone-Bannock Tribes
Shoshone-Bannock Tribes
Salish and Kootenai Confederated Tribes
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Boundary Creek (IDFG) | ALFD-WL-68 | ID | Kootenai | Boundary | Q1 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  |  | 44.5129, -114.173 |  | 673000 | 2001 | 2000-10-06
Idaho Department of Fish and Game (IDFG) | Boyle Ranch | SIDHO-WL-1 | ID | Snake Upper | Jefferson |  | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , | 2591.0 | Fee Title | 44.5129, -114.173 |  | 5200000 | 1999 | 1999-03-03
Colville Confederated Tribes | Tribal Data
Columbia Land Trust | Brix Bay-Deep River (Clough) | COLSR-WL-16 | WA | Grays | Wahkiakum | Q3 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , | 1.3 | New Easement | 44.5129, -114.173 | 90000 | 82458 | 2018 | 2018-04-27
Columbia Land Trust | Brix Bay-Deep River (Nelson) | COLSR-WL-12 | WA | Grays | Wahkiakum | Q4 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , | 29.9 | New Easement | 44.5129, -114.173 | 45000 | 36373 | 2015 | 2015-09-16
Oregon Department of Fish and Wildlife | Burlington Bottoms | BRLTN-WL | OR | Columbia Lower | Multnomah |  | COMPLETED | 1991-078-00 | John R. Palensky Wildlife Area | Exp | John Baugher | , |  | Fee Title | 44.5129, -114.173 |  | 381283 | 1992 | 1991-10-25 |  |  | 1991-11-23 |  |  | 1991-06-27
Salish and Kootenai Confederated Tribes | Tribal Data
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Calispel Creek #3/Pend Oreille (Kalispel Accord) | ALFD-WL-60 | WA | Pend Oreille | Pend Oreille | Q4 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Exp | Virgil Watts III | , | 40.0 | New Easement | 44.5129, -114.173 |  | 72676 | 2017 | 2017-07-28
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Calispel Creek 40 Acres - Kalispel Tribe MOA |  | WA | Pend Oreille | Pend Oreille | Q4 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  |  | 44.5129, -114.173 | 79000 | 0 | 2017 | 2017-07-26
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | CALISPELL CREEK (Carney) KT | ALFD-WL-28 | WA | Pend Oreille | Pend Oreille |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 |  | 529359 | 2007 | 2006-12-12 | 2006-12-12 | 2006-12-12 | 2006-11-27 | 2006-10-02 | 2006-12-06 | 2006-12-12
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Calispell Creek-Northeast (Twigg) KT | ALFD-WL-10 | WA | Pend Oreille | Pend Oreille |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 170.0 | Mix | 44.5129, -114.173 |  | 177348 | 2004 | 2004-02-04 |  |  |  | 2003-10-09 | 2003-11-24 | 2003-10-01
Idaho Department of Fish and Game (IDFG) | Camas Prairie (IDFG) | CMSPR-WL | ID | Snake Upper | Camas |  |  | 1995-057-00 | Southern Idaho Wildlife Mitigation | Exp | Sandra Fife | , |  | Mix | 44.5129, -114.173 |  | 102641 | 2002 | 2002-03-14
Oregon Department of Fish and Wildlife | Camp Adams | WILWF-WL-50 | OR | Willamette | Clackamas | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 181.3 | New Easement | 44.5129, -114.173 | 2100000 | 2079521 | 2018 | 2018-09-24
Oregon Department of Fish and Wildlife | Canby Ferry Landing (ODFW/City of Canby) | WILMIT-WL-2 | OR | Willamette | Clackamas | Q3 | COMPLETED | 1992-068-00 | Willamette Basin Mitigation | Exp | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 |  | 250000 | 2002 | 2002-05-17
Umatilla Confederated Tribes (CTUIR) | Tribal Data
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | CdA River (Trout-ELKHORN FLATS) CdA | ALFD-WL-37 | ID | Coeur D'Alene | Kootenai |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 | 2500000 | 2500536 | 2008 | 2008-08-27 | 2008-08-29 | 2008-08-29 | 2008-08-22 | 2008-08-20 | 2008-08-20 | 2008-05-22
Yakama Confederated Tribes | Tribal Data
Yakama Confederated Tribes
Yakama Confederated Tribes
Yakama Confederated Tribes
Idaho Department of Fish and Game (IDFG) | CENTENNIAL MARSH (IDFG) | SIDHO-WL-4 | ID | Snake Upper | Camas | Q2 | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , |  | Fee Title | 44.5129, -114.173 | 1500000 | 1485762 | 2008 | 2008-03-19 | 2008-03-20 | 2008-03-20 | 2008-03-20 | 2008-03-20 | 2008-03-20 | 2008-03-20
Idaho Department of Fish and Game (IDFG) | CENTENNIAL MARSH (IDFG) | SIDHO-WL-5 | ID | Snake Upper | Camas | Q2 | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , |  | Fee Title | 44.5129, -114.173 | 500000 | 435000 | 2008 | 2008-03-19
Oregon Department of Fish and Wildlife | Cerro Gordo | WILWF-WL-44 | OR | Willamette | Lane | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 531.7 | New Easement | 44.5129, -114.173 | 2486000 | 2089835 | 2017 | 2017-09-27
Oregon Department of Fish and Wildlife | Chahalpam | WILWF-WL-10 | OR | Willamette | Marion | Q3 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 338.0 | New Easement | 44.5129, -114.173 | 2900000 | 2900000 | 2013 | 2013-05-31
Oregon Watershed Enhancement Board | Chahalpam Acquisition | WILWF-WL-10 | OR | Willamette | Marion |  | COMPLETED | 2009-012-00 | Willamette Bi-Op Habitat Restoration | Cap | Hannah Dondy-Kaplan | , |  |  | 44.5129, -114.173 | 600000 | 600000 | 2013 | 2013-05-31
Oregon Department of Fish and Wildlife | Chahalpam Phase #3 | WILWF-WL-39 | OR | Willamette | Linn | Q2 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 33.0 | New Easement | 44.5129, -114.173 | 57000 | 90104 | 2018 | 2018-03-01
Oregon Department of Fish and Wildlife | Chahalpam Phase 2 | WILWF-WL-21 | OR | Willamette | Marion | Q2 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 91.0 | New Easement | 44.5129, -114.173 | 935000 | 959120 | 2015 | 2015-01-01 |  |  |  |  | 2014-03-28 | 2013-12-13
Oregon Department of Fish and Wildlife | Chankawan | WILWF-WL-30 | OR | Willamette | Marion | Q3 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 425.7 | New Easement | 44.5129, -114.173 | 1275000 | 1276976 | 2016 | 2016-05-20
Methow Salmon Recovery Foundation | Chewuch River Property (MSRF) | CHEWR-WL-1 | WA | Methow | Okanogan |  |  | 2007-264-00 | Methow River Complexity Fisheries Enhancement | Exp | Joseph Connor | , |  | New Easement | 44.5129, -114.173 |  | 182000 | 2009 | 2008-12-05 |  |  | 2009-09-28 |  | 2009-05-04 | 2008-10-01
Washington Department of Fish and Wildlife (WDFW) | Chinook Acquisition | CHRES-WL-1 | WA | Columbia Estuary | Pacific | Q4 | COMPLETED | 2010-070-00 | WA Estuary MOA Project Scoping & Implementation | Exp | Jason Karnezis | , |  | New Easement | 44.5129, -114.173 | 550000 | 572469 | 2013 | 2013-09-26 |  |  | 2013-09-20 | 2013-09-09 | 2013-09-11 | 2012-10-01
Washington Department of Fish and Wildlife (WDFW) | Chinook River #2/Martin (WDFW) | COLSR-WL-17 | WA | Columbia Estuary | Pacific | Q2 | COMPLETED | 2010-070-00 | WA Estuary MOA Project Scoping & Implementation | Exp | Jason Karnezis | , | 1.7 | Fee Title | 44.5129, -114.173 | 170000 | 170000 | 2019 | 2019-02-15
Shoshone-Bannock Tribes | Tribal Data
Shoshone-Bannock Tribes
Nature Conservancy | Coburg Ridge Easement (TNC) | CBRGR-WL-1 | OR | Willamette | Lane |  | COMPLETED | 2007-260-00 | Upland Prairie/Oak Habitat Protection | Cap | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 | 4900500 | 4900500 | 2007 | 2007-05-23 | 2007-05-23 | 2007-05-23 | 2007-05-23 | 2007-05-23 | 2007-06-06 | 2006-10-01
Salish and Kootenai Confederated Tribes | Tribal Data
Nez Perce Tribe
Nez Perce Tribe
Oregon Department of Fish and Wildlife | Cornerstone Project | WILWF-WL-37 | OR | Willamette | Polk | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 86.7 | New Easement | 44.5129, -114.173 | 490000 | 354776 | 2016 | 2016-09-28
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | COUGAR CREEK (CdA River) CdA | ALFD-WL-24 | ID | Coeur D'Alene | Shoshone |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 |  | 1504341 | 2007 | 2006-10-02 | 2006-10-02 | 2006-10-02 | 2006-10-02 | 2006-10-02 | 2006-10-02 | 2006-10-02
Oregon Department of Fish and Wildlife | Courtney Creek | WILWF-WL-40 | OR | Willamette | Linn | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 202.7 | New Easement | 44.5129, -114.173 | 545000 | 556166 | 2017 | 2017-08-08
Salish and Kootenai Confederated Tribes | Tribal Data
Oregon Department of Fish and Wildlife | Coyote Creek | WILWF-WL-9 | OR | Willamette | Lane | Q2 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 309.0 | New Easement | 44.5129, -114.173 | 805000 | 805137 | 2013 | 2013-03-15 |  |  |  |  | 2012-09-11
Oregon Department of Fish and Wildlife | Coyote Creek NE - Campbell | WILWF-WL-24 | OR | Willamette | Lane | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 34.5 | New Easement | 44.5129, -114.173 | 95000 | 95788 | 2015 | 2015-08-26
Oregon Department of Fish and Wildlife | Coyote Creek NE - Jackson | WILWF-WL-25 | OR | Willamette | Lane | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 191.3 | New Easement | 44.5129, -114.173 | 533000 | 535276 | 2015 | 2015-08-26
Oregon Department of Fish and Wildlife | Coyote Oaks | WILWF-WL-17 | OR | Willamette | Lane | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 151.7 | New Easement | 44.5129, -114.173 | 304000 | 318372 | 2014 | 2014-09-26 |  |  |  |  | 2014-05-19 | 2014-02-06
Lower Columbia Estuary Partnership | Crazy Johnson Creek (Columbia Land Trust) | CJHNK-WL-1 | WA | Grays | Wahkiakum |  | COMPLETED | 2003-011-00 | Columbia River Estuary Habitat Restoration | Exp | Anne Creason | , |  | New Easement | 44.5129, -114.173 |  | 362431 | 2009 | 2009-04-01 |  |  | 2009-03-27 | 2009-03-13 | 2009-03-25 | 2009-02-16
Columbia Land Trust | Crooked Creek (White) | COLSR-WL-10 | WA | Grays | Wahkiakum | Q1 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , | 19.0 | New Easement | 44.5129, -114.173 | 56000 | 57325 | 2015 | 2014-12-19
Columbia Land Trust | Crooked Creek-#2 Miller-south | COLSR-WL-14 | WA | Grays | Wahkiakum | Q2 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , | 31.0 | New Easement | 44.5129, -114.173 | 61000 | 62924 | 2017 | 2017-01-06
Columbia Land Trust | CSR (Tide Creek) | COLSR-WL-7 | OR | Columbia Lower | Columbia | Q1 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , |  | New Easement | 44.5129, -114.173 | 160000 | 160891 | 2013 | 2012-12-28
Salish and Kootenai Confederated Tribes | Tribal Data
Umatilla Confederated Tribes (CTUIR)
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | DEEP CREEK-Boundary Creek/McArthur Wildlife Corridor (Palaniuk) IDFG | ALFD-WL-15 | ID | Kootenai | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 39.9 | Mix | 44.5129, -114.173 |  | 65277 | 2005 | 2005-07-21 |  |  |  | 2005-02-15 | 2005-02-09 | 2005-06-14
Lower Columbia Estuary Partnership | DEEP RIVER-Olsen (CLT) | COLSR-WL-3 | WA | Grays | Wahkiakum |  | COMPLETED | 2003-011-00 | Columbia River Estuary Habitat Restoration | Exp | Anne Creason | , |  | New Easement | 44.5129, -114.173 | 115000 | 114252 | 2012 | 2012-02-15 | 2012-02-15 | 2012-02-15 | 2012-02-15 | 2012-02-15 | 2012-02-15 | 2012-02-15
Idaho Department of Fish and Game (IDFG) | Deer Park WMA-Allen (BLM) | SFSR-WL-5 | ID | Snake Upper | Jefferson | Q1 | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Exp | Sandra Fife | , |  | New Easement | 44.5129, -114.173 |  | 283800 | 2003 | 2002-11-15
Idaho Department of Fish and Game (IDFG) | Deer Park WMA-Horkley (BLM) | SFSR-WL-6 | ID | Snake Upper | Jefferson | Q1 | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Exp | Sandra Fife | , |  | New Easement | 44.5129, -114.173 |  | 336000 | 2003 | 2002-11-15
Idaho Department of Fish and Game (IDFG) | Deer Parks Wildlife Mitigation Area | SFSR-WL-5 | ID | Snake Upper | Jefferson |  | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , | 81.0 | Fee Title | 44.5129, -114.173 |  | 283800 | 2003 | 2002-11-14
Idaho Department of Fish and Game (IDFG) | Deer Parks Wildlife Mitigation Area | SFSR-WL-6 | ID | Snake Upper | Jefferson |  | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , | 120.1 | Fee Title | 44.5129, -114.173 |  | 336000 | 2003 | 2002-11-18
Salish and Kootenai Confederated Tribes | Tribal Data
Montana Fish, Wildlife and Parks (MFWP) | Diamond B (HHDMT-WL-11) | HHDMT-WL-11 | MT | Flathead | Flathead |  | COMPLETED | 2008-800-00 | Montana Resident Fish Habitat Aquisition | Cap | Cecilia Brown | , |  | New Easement | 44.5129, -114.173 | 809250 | 312317 | 2012 | 2011-12-29 | 2011-12-29 | 2011-12-29 | 2011-12-21 | 2011-12-15 | 2011-12-09 | 2011-10-01
Salish and Kootenai Confederated Tribes | Tribal Data
Salish and Kootenai Confederated Tribes
Yakama Confederated Tribes
Nez Perce Tribe
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Montana Fish, Wildlife and Parks (MFWP) | Elk Creek (CSKT) | ELKCK-WL-1 | MT | Flathead | Missoula | Q4 | COMPLETED | 1991-019-03 | Hungry Horse Mitigation Habitat Restoration and Research, Monitoring and Evaluation (RM&E) | Cap | Cecilia Brown | , | 80.0 | New Easement | 44.5129, -114.173 |  | 5000000 | 2006 | 2006-09-18
Columbia Land Trust | Elochoman #3 - Longtain | ELMNR-WL-2 | WA | Elochoman | Wahkiakum | Q4 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , | 34.3 | New Easement | 44.5129, -114.173 | 78000 | 87720 | 2018 | 2018-09-26
Columbia Land Trust | Elochoman 3--Oxbow/AGR | ELMNR-WL-4 | WA | Elochoman | Wahkiakum | Q2 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , | 29.8 | Fee Title | 44.5129, -114.173 | 87000 | 93545 | 2019 | 2019-03-11
Columbia Land Trust | Elochoman 3--Powerline/Doumit | ELMNR-WL-3 | WA | Elochoman | Wahkiakum | Q2 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , | 59.3 | Fee Title | 44.5129, -114.173 | 180000 | 182433 | 2019 | 2019-02-08
Columbia Land Trust | Elochoman Poplar Lease | COLSR-WL-5 | WA | Elochoman | Wahkiakum | Q1 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , |  |  | 44.5129, -114.173 | 40000 | 40308 | 2016 | 2015-12-04
Columbia Land Trust | Elochoman-Thomas#2 Acquisition | COLSR-WL-5 | WA | Elochoman | Wahkiakum | Q1 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , |  | New Easement | 44.5129, -114.173 | 335000 | 267147 | 2013 | 2012-11-15 |  |  |  |  | 2012-10-01 | 2012-10-01
Oregon Department of Fish and Wildlife | Eola Hills/Zena Addition East (TPL/ODFW) | WILMIT-WL-8 | OR | Willamette | Polk |  |  | 1992-068-00 | Willamette Basin Mitigation | Cap | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 | 373600 | 373600 | 2008 | 2008-09-25
Oregon Department of Fish and Wildlife | Eola Hills/Zena Addition West (TPL/ODFW) | WILMIT-WL-9 | OR | Willamette | Polk |  |  | 1992-068-00 | Willamette Basin Mitigation | Cap | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 | 1115903 | 1115903 | 2008 | 2008-09-25
Nez Perce Tribe | Tribal Data | [8 empty] | Exp | Jonathan McCloud | , |  |  | 44.5129, -114.173 |  | 980 | 2018 | 2017-11-21
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Oregon Department of Fish and Wildlife | Finn Rock Reach | WILWF-WL-43 | OR | Willamette | Lane | Q1 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 303.0 | New Easement | 44.5129, -114.173 | 1415000 | 1456264 | 2018 | 2017-12-14
Salish and Kootenai Confederated Tribes | Tribal Data
Oregon Department of Fish and Wildlife | Flight's End Property | WILWF-WL-11 | OR | Columbia Lower | Columbia | Q4 |  | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 100.0 | New Easement | 44.5129, -114.173 | 665000 | 782662 | 2013 | 2013-09-24 |  |  | 2013-09-10 | 2013-08-30 | 2013-03-20 | 2012-10-01
Yakama Confederated Tribes | Tribal Data
Umatilla Confederated Tribes (CTUIR)
Spokane Tribe
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Idaho Department of Fish and Game (IDFG) | Georgetown Summit Cost Share (IDFG) | SIDHO-WL-26 | ID |  | Bear Lake | Q2 | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , | 760.0 | New Easement | 44.5129, -114.173 | 891000 | 446569 | 2016 | 2016-03-16
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Goodner Ray Family Trust (KT) | KALTRIBE-WL-4 | ID | Pend Oreille | Bonner | Q4 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Exp | Virgil Watts III | , |  |  | 44.5129, -114.173 |  | 686385 | 2002 | 2002-09-30
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Goose Haven Lake-Bader/St. Maries (CdA) | ALFD-WL-1 | ID | Coeur D'Alene | Benewah | Q2 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Exp | Virgil Watts III | , | 647.6 | New Easement | 44.5129, -114.173 |  | 800324 | 2002 | 2002-01-03 |  |  | 2001-12-31 | 2001-10-25
Columbia Land Trust | Grays Bay-Deep River Hancock | COLSR-WL-9 | WA | Grays | Wahkiakum | Q3 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , | 80.4 | New Easement | 44.5129, -114.173 | 150000 | 121733 | 2014 | 2014-04-02 |  |  | 2014-04-01 | 2014-02-04 | 2013-10-31 | 2013-10-01
Columbia Land Trust | Grays River Confluence #1 (Matteson Road) | COLSR-WL-8 | WA | Grays | Wahkiakum | Q1 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , | 113.0 | New Easement | 44.5129, -114.173 | 405000 | 405685 | 2014 | 2013-12-16 |  |  | 2013-10-01 | 2013-10-01 | 2013-10-11 | 2013-10-01
Oregon Department of Fish and Wildlife | Green Island (MRT) | GRNIL-WL-1 | OR | Willamette | Lane | Q4 | COMPLETED | 1992-068-00 | Willamette Basin Mitigation | Cap | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 |  | 1052826 | 2004 | 2004-09-27
National Fish and Wildlife Foundation | Hancock Springs MC Conservation Easement | HNKSP-WL-1 | WA | Methow | Okanogan |  | COMPLETED | 2002-013-01 | Water Entity - CBWTP | Exp | Maura Eagan Moody | , |  | New Easement | 44.5129, -114.173 |  | 500000 | 2005 | 2005-09-15 | 2005-09-01 | 2005-09-15
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Hangman Creek (Felsman) CdA | HNGCK-WL-1 | ID | Spokane | Benewah | Q2 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 |  | 600000 | 2005 | 2005-01-07
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Hangman Creek (Hanson) CdA | HNGCK-WL-3 | ID | Spokane | Benewah | Q1 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 |  | 1391392 | 2005 | 2004-12-13
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Hangman Creek (Kitt) CdA | HNGCK-WL-2 | ID | Spokane | Benewah | Q4 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 |  | 20951 | 2005 | 2005-09-02
Oregon Department of Fish and Wildlife | Harkens Lake (Adams) (WILWF-WL-5) | WILWF-WL-5 | OR | Willamette | Linn |  | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , |  |  | 44.5129, -114.173 | 47250 | 47250 | 2012 | 2011-12-19
Oregon Department of Fish and Wildlife | Harkens Lake (Horning) (WILWF-WL-4) | WILWF-WL-4 | OR | Willamette | Linn | Q1 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , |  |  | 44.5129, -114.173 | 246300 | 246300 | 2012 | 2011-12-19
Oregon Department of Fish and Wildlife | Harkens Lake (Pitcher) WILWF-WL-06 | WILWF-WL-6 | OR | Willamette | Linn |  | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , |  |  | 44.5129, -114.173 | 33000 | 33000 | 2012 | 2012-02-08
Oregon Department of Fish and Wildlife | Harkens Lake South Access | WILF-WL-41 | OR | Willamette | Benton | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 15.4 | New Easement | 44.5129, -114.173 | 115500 | 117392 | 2017 | 2017-09-21
Colville Confederated Tribes | Tribal Data
Bonneville Power Administration, Upper Columbia Salmon Recovery Board | Harrison Property - Compensation for removal of 40 pear trees |  | WA | Entiat | Chelan | Q2 | COMPLETED | 2010-001-00 | Upper Columbia Programmatic Habitat | Exp | Joseph Connor | , |  |  | 44.5129, -114.173 | 14555 | 14555 | 2015 | 2015-02-27 | 2015-09-29 | 2015-09-16
Salish and Kootenai Confederated Tribes | Tribal Data
Salish and Kootenai Confederated Tribes
Oregon Department of Fish and Wildlife | Hayden Island (Gail Achterman Wildlife Area) | WILWF-WL-26 | OR | Willamette | Polk | Q3 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 264.9 | New Easement | 44.5129, -114.173 | 1500000 | 1500000 | 2016 | 2016-05-25
National Fish and Wildlife Foundation | Heath MC Conservation Easement | HEATH-WL-1 |  |  |  |  | COMPLETED | 2002-013-01 | Water Entity - CBWTP | Exp | Maura Eagan Moody | , |  |  | 44.5129, -114.173 |  | 1000000 | 2006 | 2006-08-25 | 2006-08-25 | 2006-08-25
Oregon Department of Fish and Wildlife | Herbert Farm (City of Corvallis/ODFW) | WILMIT-WL-3 | OR | Willamette | Benton | Q3 | COMPLETED | 1992-068-00 | Willamette Basin Mitigation | Exp | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 |  | 387500 | 2002 | 2002-06-17
Salish and Kootenai Confederated Tribes | Tribal Data
Umatilla Confederated Tribes (CTUIR)
Oregon Department of Fish and Wildlife | Horseshoe Lake (Carnegie) (WILWF-WL-1) | WILWF-WL-1 | OR | Willamette | Linn |  | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , |  | New Easement | 44.5129, -114.173 |  | 1200 | 2012 | 2012-08-16
Oregon Department of Fish and Wildlife | Horseshoe Lake (Stellmacher) (WILWF-WL-2) | WILWF-WL-2 | OR | Willamette | Linn |  | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , |  | New Easement | 44.5129, -114.173 |  | 11250 | 2012 | 2012-08-16
Oregon Department of Fish and Wildlife | Horseshoe Lake (Waggle) WILWF-WL-3 | WILWF-WL-3 | OR | Willamette | Linn |  | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , |  | New Easement | 44.5129, -114.173 | 38100 | 38100 | 2012 | 2012-08-16
Salish and Kootenai Confederated Tribes | Tribal Data
Yakama Confederated Tribes
Spokane Tribe
Spokane Tribe
Spokane Tribe
Spokane Tribe
Spokane Tribe
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Indian Creek/Pend Oreille/Jacobson #2 (Kalispel Tribe) 2nd Payment | ALFD-WL-54 | WA | Pend Oreille | Pend Oreille | Q1 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 178.0 | New Easement | 44.5129, -114.173 |  | 348570 | 2013 | 2012-10-04
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Indian Creek/Pend Oreille/Jacobson#2 (Kalispel Tribe) | ALFD-WL-54 | WA | Pend Oreille | Pend Oreille |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 | 971102 | 928718 | 2012 | 2012-09-26
Colville Confederated Tribes | Tribal Data | [8 empty] | Cap | Joe Deherrera | , |  | New Easement | 44.5129, -114.173 |  | 1024200 | 2007 | 2007-09-26
Salish and Kootenai Confederated Tribes | [9 empty] | Cap | Cecilia Brown | , | 1.5 | New Easement | 44.5129, -114.173 | 80000 | 80801 | 2016 | 2016-06-16
Salish and Kootenai Confederated Tribes | [9 empty] | Cap | Cecilia Brown | , |  | New Easement | 44.5129, -114.173 | 103525 | 103525 | 2012 | 2011-10-04 | 2011-10-04 | 2011-10-04 | 2011-10-04 | 2011-10-04 | 2011-10-04 | 2011-10-04
Yakama Confederated Tribes | [9 empty] | Exp | Michelle O'Malley | , |  | New Easement | 44.5129, -114.173 | 1525000 | 1530309 | 2011 | 2011-03-08 | 2011-03-08 | 2011-03-08 | 2011-03-08 | 2011-03-08 | 2011-03-08 | 2011-03-08
Yakama Confederated Tribes | [9 empty] | Exp | Michelle O'Malley | , |  | New Easement | 44.5129, -114.173 | 527000 | 516999 | 2011 | 2011-03-07 | 2011-03-07 | 2011-03-07 | 2011-03-07 | 2011-03-07 | 2011-03-07 | 2011-03-07
Salish and Kootenai Confederated Tribes | [9 empty] | Cap | Cecilia Brown | , |  |  | 44.5129, -114.173 |  | 258195 | 2006 | 2006-09-25
US Fish and Wildlife Service (USFWS) | Kaniksu Addition | LPNWR-WL-1 |  |  |  |  | COMPLETED | 1993-058-00 | Wa Coalition Mitigation Agreem | Exp | Joe Deherrera | , |  |  | 44.5129, -114.173 |  | 314439 | 2000 | 2000-08-18
Columbia Land Trust | Kerry Island Acquisition | COLSR-WL-6 | OR | Columbia Estuary | Columbia | Q3 | COMPLETED | 2010-073-00 | Columbia Land Trust Estuarine Restoration | Exp | Anne Creason | , |  | New Easement | 44.5129, -114.173 | 320000 | 320637 | 2013 | 2013-04-30 |  |  | 2012-12-15 | 2013-03-11 | 2012-10-17 | 2012-10-01
Salish and Kootenai Confederated Tribes | Tribal Data
Lower Columbia Estuary Partnership | Knappton Cove (CLT) | COLSR-WL-4 | WA | Grays | Pacific |  | COMPLETED | 2003-011-00 | Columbia River Estuary Habitat Restoration | Exp | Anne Creason | , |  | New Easement | 44.5129, -114.173 | 452000 | 255757 | 2012 | 2012-03-29
Montana Fish, Wildlife and Parks (MFWP) | Kokanee Bend South (Lapp) | HHDMT-WL-12 | MT | Flathead | Flathead | Q4 | COMPLETED | 2008-800-00 | Montana Resident Fish Habitat Aquisition | Cap | Cecilia Brown | , |  | New Easement | 44.5129, -114.173 | 640000 | 642763 | 2013 | 2013-09-25 | 2013-09-01 | 2013-07-01 | 2013-09-17 | 2013-09-06 | 2013-03-27 | 2013-02-04
Oregon Department of Fish and Wildlife | Ladd Marsh Additions (TNC/ODFW) | LADD-WL-1 |  |  |  | Q3 | COMPLETED | 2000-021-00 | Ladd Marsh Wildlife Mitigation | Exp | Tracy Hauser | , |  | Mix | 44.5129, -114.173 |  | 330355 | 2001 | 2001-05-07
Idaho Department of Fish and Game (IDFG) | land (name TBD) |  |  |  |  | Q4 | COMPLETED | 1992-040-00 | Redfish Lake Sockeye Broodstock | Exp | Gregory Baesler | , |  |  | 44.5129, -114.173 |  | 577085 | 2004 | 2004-09-28
Yakama Confederated Tribes | Tribal Data
Yakama Confederated Tribes
Nez Perce Tribe
Yakama Confederated Tribes
Nez Perce Tribe
Nez Perce Tribe
Nez Perce Tribe
Nez Perce Tribe
Nez Perce Tribe
Yakama Confederated Tribes
Yakama Confederated Tribes
Yakama Confederated Tribes
Yakama Confederated Tribes
Yakama Confederated Tribes
Salish and Kootenai Confederated Tribes
Shoshone-Bannock Tribes
Shoshone-Bannock Tribes
Shoshone-Bannock Tribes
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Oregon Department of Fish and Wildlife | Little Sweden Conservation Area | WILWF-WL-46 | OR | Willamette | Marion | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 183.7 | New Easement | 44.5129, -114.173 | 700000 | 495967 | 2017 | 2017-09-27
US Fish and Wildlife Service (USFWS) | Logan Valley | MALRIVER-WL-1 | OR | Malheur | Grant |  | COMPLETED | 1997-059-00 | Or W/L Plan And Coordination | Cap | Joe Deherrera | , | 1760.0 | Fee Title | 44.5129, -114.173 |  | 2003708 | 2000 | 2000-03-06
Umatilla Confederated Tribes (CTUIR) | Tribal Data
Salish and Kootenai Confederated Tribes
Yakama Confederated Tribes
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Lower Pack River (Gold Creek) IDFG | ALFD-WL-20 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 310.0 | Mix | 44.5129, -114.173 |  | 2326259 | 2006 | 2005-11-29 |  |  |  | 2005-10-01
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Lower Pack River (IDFG) | ALFD-WL-66 | ID | Pend Oreille | Bonner | Q1 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  |  | 44.5129, -114.173 |  | 42500 | 2000 | 1999-10-04
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | LOWER PACK RIVER (Liu lot) IDFG | ALFD-WL-23 | ID | Pend Oreille | Bonner |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 |  | 40336 | 2007 | 2007-03-09 | 2007-03-09 | 2007-03-09 | 2007-03-09 | 2007-03-09 | 2007-03-09 | 2007-03-09
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | LOWER PACK RIVER (Wilson Ranch) IDFG | ALFD-WL-33 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 |  | 45311 | 2008 | 2007-11-19 |  |  | 2007-11-12 | 2007-10-12 | 2007-11-13
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | LOWER PACK RIVER - Connor Lot | ALFD-WL-22 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 0.3 | Mix | 44.5129, -114.173 |  | 22670 | 2006 | 2006-06-26 |  |  |  | 2006-03-30 | 2006-03-16 | 2006-03-13
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Lower Pack River-Shields (RAPID LIGHTNING-Pack River Ridge) IDFG | ALFD-WL-14 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 41.0 | Fee Title | 44.5129, -114.173 |  | 461861 | 2006 | 2006-06-26 |  |  |  | 2006-03-07 | 2005-12-16 | 2005-11-07
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Lower Pack River/Rapid Lighting Creek/Ginter#3 (IDFG) | ALFD-WL-53 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 | 325000 | 325515 | 2012 | 2012-06-26 | 2012-06-27 | 2012-06-27 | 2012-06-27 | 2012-06-27 | 2012-06-27 | 2012-06-27
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | LOWER ST. JOE (Martin) IDFG | ALFD-WL-26 | ID | Coeur D'Alene | Benewah |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 |  | 621549 | 2007 | 2007-03-08 |  |  | 2007-02-28
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Lower Trimble Creek/Trimble-Scheibel | NIDAHO-WL | WA | Pend Oreille | Pend Oreille | Q4 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Exp | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 |  |  | 2001 | 2001-09-30
Burns-Paiute Tribe | Tribal Data
Salish and Kootenai Confederated Tribes | [9 empty] | Exp | Cecilia Brown | , |  | New Easement | 44.5129, -114.173 |  | 160000 | 2010 | 2010-08-16
Colville Confederated Tribes | [9 empty] | Exp | Maura Eagan Moody | , | 154.5 | New Easement | 44.5129, -114.173 | 849450 | 852075 | 2013 | 2013-09-25 |  |  | 2013-09-17 | 2013-09-06 | 2013-01-15 | 2012-11-07
Spokane Tribe | [9 empty] | Cap | Wynn Avocette | , | 85.0 | Fee Title | 44.5129, -114.173 |  | 60545 | 2004 | 2004-03-26
Spokane Tribe | [9 empty] | Exp | Wynn Avocette | , |  | Fee Title | 44.5129, -114.173 |  |  | 1997 | 1997-09-24
Spokane Tribe | [9 empty] | Cap | Wynn Avocette | , | 124.6 | New Easement | 44.5129, -114.173 |  | 116187 | 2004 | 2004-09-28
Spokane Tribe | [9 empty] | Exp | Wynn Avocette | , |  | Fee Title | 44.5129, -114.173 |  |  | 1998 | 1997-10-31
Spokane Tribe | [9 empty] | Cap | Wynn Avocette | , | 565.8 | New Easement | 44.5129, -114.173 |  | 557943 | 2004 | 2004-03-26
Spokane Tribe | [9 empty] | Cap | Wynn Avocette | , | 35.0 | New Easement | 44.5129, -114.173 |  | 46049 | 2006 | 2005-11-30
Spokane Tribe | [9 empty] | Cap | Wynn Avocette | , | 96.0 | New Easement | 44.5129, -114.173 |  | 95813 | 2006 | 2006-01-27
National Fish and Wildlife Foundation | MID-METHOW CONSERVATION EASEMENT (Lehman Riparian Project) | LEMAN-WL-1 | WA | Methow | Okanogan |  |  | 2002-013-01 | Water Entity - CBWTP | Exp | Maura Eagan Moody | , |  | New Easement | 44.5129, -114.173 | 415000 | 415000 | 2008 | 2008-03-21 | 2008-05-01 | 2008-05-01 | 2008-05-01 | 2008-05-01 | 2008-05-01 | 2008-05-01 | 48.402872 | 48.402872 | 48.396132 | 48.396132 | -120.138642 | -120.138642 | -120.138950 | -120.138950
Oregon Department of Fish and Wildlife | Minto Island Conservation Area Property | WILWF-WL-14 | OR | Willamette | Marion | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 307.0 | New Easement | 44.5129, -114.173 | 850000 | 837330 | 2013 | 2013-09-26 |  |  | 2013-09-23 | 2013-08-19 | 2013-05-07 | 2012-12-06
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Mirror Lake/Woldson/Bonners Ferry (Kootenai) | ALFD-WL-49 | ID | Kootenai | Boundary |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 | 165000 | 150375 | 2012 | 2012-09-13
Oregon Department of Fish and Wildlife | Misc. - Fees/Annual Lease PDFF-FF-1 |  |  |  |  | Q1 | COMPLETED | 1988-053-08 | Hood River Production Operations and Maintenance (O&M) and Powerdale | Exp | Eric Leitzinger | , |  |  | 44.5129, -114.173 | 255 | 255 | 2011 | 2010-10-25
Nez Perce Tribe | Tribal Data
Nez Perce Tribe
Salish and Kootenai Confederated Tribes
Oregon Department of Fish and Wildlife | Miscellaneous fees & lease fees |  |  |  |  | Q4 | COMPLETED | 1988-053-08 | Hood River Production Operations and Maintenance (O&M) and Powerdale | Exp | Eric Leitzinger | , |  |  | 44.5129, -114.173 |  | 508 | 2008 | 2008-09-15
Nez Perce Tribe | Tribal Data
Nez Perce Tribe
Nez Perce Tribe
Colville Confederated Tribes
Oregon Department of Fish and Wildlife | Mt Richmond | WILWF-WL-12 | OR | Willamette | Yamhill | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 284.7 | New Easement | 44.5129, -114.173 | 845000 | 845850 | 2013 | 2013-09-13 |  |  | 2013-08-27 | 2013-07-29 | 2013-03-26 | 2013-01-31
Salish and Kootenai Confederated Tribes | Tribal Data
Oregon Department of Fish and Wildlife | Muddy Valley Habitat Reserve | WILWF-WL-38 | OR | Willamette | Yamhill | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 540.0 | New Easement | 44.5129, -114.173 | 3700000 | 2712411 | 2016 | 2016-09-28
Oregon Department of Fish and Wildlife | Mulkey Ridge | WILWF-WL-29 | OR | Willamette | Benton | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 170.0 | New Easement | 44.5129, -114.173 | 825000 | 847500 | 2015 | 2015-09-10
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Naccarato Family (Kalispel Tribe) | KALTRIBE-WL-1 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Exp | Virgil Watts III | , |  | Mix | 44.5129, -114.173 |  | 80054 | 2000 | 2000-05-26
Yakama Confederated Tribes | Tribal Data
Oregon Department of Fish and Wildlife | Noble Oaks | WILWF-WL-19 | OR | Willamette | Polk | Q1 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 471.3 | New Easement | 44.5129, -114.173 | 2310000 | 1501582 | 2015 | 2014-10-03 |  |  |  |  | 2014-06-30 | 2014-05-21
Oregon Department of Fish and Wildlife | Noble Oaks Preserve Additions #2 (Kirkham) | WILWF-WL-36 | OR | Willamette | Polk | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 191.0 | New Easement | 44.5129, -114.173 | 695000 | 720015 | 2016 | 2016-09-28
Oregon Department of Fish and Wildlife | Noble/LONESTAR (GLT) | WILMIT-WL-6 | OR | Willamette | Benton |  |  | 1992-068-00 | Willamette Basin Mitigation | Cap | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 | 2500000 | 2414000 | 2008 | 2008-02-28 | 2008-02-29 | 2008-02-29 | 2008-02-29 | 2008-02-29 | 2008-02-29 | 2008-02-29
Salish and Kootenai Confederated Tribes | Tribal Data
Salish and Kootenai Confederated Tribes
Montana Fish, Wildlife and Parks (MFWP) | North Shore FMA (Worm) | HHDMT-WL-13 | MT | Flathead | Flathead | Q1 | COMPLETED | 2008-800-00 | Montana Resident Fish Habitat Aquisition | Cap | Cecilia Brown | , | 189.0 | New Easement | 44.5129, -114.173 | 1610425 | 1610425 | 2014 | 2014-02-28 |  |  | 2014-02-21 | 2013-10-01 | 2013-11-13 | 2013-10-31
Salish and Kootenai Confederated Tribes | Tribal Data
Yakama Confederated Tribes
Washington Department of Fish and Wildlife (WDFW) | Okanogan-Similkameen (Cutchie) | OSKIM-WL-4 | WA | Okanogan | Okanogan |  | COMPLETED | 2007-232-00 | Okanogan-Similkameen Habitat Acquisition | Cap | David Roberts | , |  | New Easement | 44.5129, -114.173 | 2351437 | 2365285 | 2012 | 2012-09-24
Colville Confederated Tribes | Tribal Data
Colville Confederated Tribes
Colville Confederated Tribes
Salish and Kootenai Confederated Tribes
Montana Fish, Wildlife and Parks (MFWP) | Otter Island Addition 1 | HHDMT-WL-15 | MT | Flathead | Flathead | Q2 | COMPLETED | 2008-800-00 | Montana Resident Fish Habitat Aquisition | Cap | Cecilia Brown | , | 13.6 | New Easement | 44.5129, -114.173 | 127000 | 105045 | 2015 | 2015-03-03
Montana Fish, Wildlife and Parks (MFWP) | Otter Island Addition 2 | HHDMT-WL-14 | MT | Flathead | Flathead | Q2 | COMPLETED | 2008-800-00 | Montana Resident Fish Habitat Aquisition | Cap | Cecilia Brown | , | 6.1 | New Easement | 44.5129, -114.173 | 73000 | 49229 | 2015 | 2015-03-03
Confederated Tribes of Warm Springs | Tribal Data
Confederated Tribes of Warm Springs
Spokane Tribe
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Pend Oreille River-Albeni Cove (Anselmo) IDFG | ALFD-WL-35 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 | 163500 | 163799 | 2008 | 2008-09-02 | 2008-08-30 | 2008-08-30 | 2008-08-25 | 2008-07-09 | 2008-08-25 | 2008-08-01
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Perkins Lake-Moyie Springs (KToI) | ALFD-WL-6 | ID | Kootenai | Boundary | Q4 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Exp | Virgil Watts III | , | 98.0 | New Easement | 44.5129, -114.173 |  | 203639 | 2002 | 2002-09-26 |  |  |  | 2002-02-11
Montana Fish, Wildlife and Parks (MFWP) | PERRY CREEK (Swan Valley) | SWNVY-WL-3 | MT | Flathead | Lake |  | COMPLETED | 2008-800-00 | Montana Resident Fish Habitat Aquisition | Cap | Cecilia Brown | , |  | New Easement | 44.5129, -114.173 | 1037086 | 1037086 | 2012 | 2011-10-03 | 2011-10-03 | 2011-10-03 | 2011-10-03 | 2011-10-03 | 2011-10-03 | 2011-10-03
Salish and Kootenai Confederated Tribes | Tribal Data
Confederated Tribes of Warm Springs
Confederated Tribes of Warm Springs
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Montana Fish, Wildlife and Parks (MFWP) | Plum Creek Timberlands (W.Swan Valley) | SWNVY-WL-1 | MT | Flathead | Lake |  | COMPLETED | 2008-800-00 | Montana Resident Fish Habitat Aquisition | Cap | Cecilia Brown | , |  | New Easement | 44.5129, -114.173 |  | 9750112 | 2011 | 2010-12-01 | 2010-12-01 | 2010-12-01 | 2010-12-01 | 2010-12-01 | 2010-12-01 | 2010-12-01
Montana Fish, Wildlife and Parks (MFWP) | Plum Creek/North Swan Valley (MFWP) | SWNVY-WL-1 | MT | Flathead | Lake | Q4 | COMPLETED | 1991-019-03 | Hungry Horse Mitigation Habitat Restoration and Research, Monitoring and Evaluation (RM&E) | Cap | Cecilia Brown | , | 7203.6 | New Easement | 44.5129, -114.173 |  | 1100000 | 2006 | 2006-08-31
Salish and Kootenai Confederated Tribes | Tribal Data
Salish and Kootenai Confederated Tribes
Idaho Governor's Office of Species Conservation | Pratt Creek | UPLER-WL-7 | ID | Salmon | Lemhi | Q3 | COMPLETED | 2010-088-00 | Upper and Lower Lemhi Acquisition/Easements | Exp | Hannah Dondy-Kaplan | , | 2316.0 | New Easement | 44.5129, -114.173 | 2435000 | 2438220 | 2017 | 2017-04-18
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Priest River-Carey Creek/Courchaine (KT) | ALFD-WL-2 | ID | Pend Oreille | Bonner | Q1 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Exp | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 |  | 450852 | 2002 | 2001-12-20
Salish and Kootenai Confederated Tribes | Tribal Data
Washington Department of Fish and Wildlife (WDFW) | Provide cost share funds for Cowiche conservation easement |  | WA | Yakima | Yakima |  | COMPLETED | 2007-113-00 | Cowiche Restore And Protect | Exp | Jay Marcotte | , |  | New Easement | 44.5129, -114.173 |  | 0 | 2007 | 2008-09-29 | 2008-09-29 | 2008-09-29 | 2008-09-29 | 2008-09-29 | 2008-09-29 | 2008-09-29 | 46.651790 |  | 46.629019 |  | -120.844966 |  | -120.870519
Oregon Department of Fish and Wildlife | Railroad Island | WILWF-WL-8 | OR | Willamette | Linn |  | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , |  | New Easement | 44.5129, -114.173 | 54000 | 52986 | 2012 | 2012-09-21
Oregon Department of Fish and Wildlife | Rainbow Farms | WILWF-WL-28 | OR | Willamette | Washington | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 76.1 | New Easement | 44.5129, -114.173 | 375000 | 381710 | 2015 | 2015-09-03
Umatilla Confederated Tribes (CTUIR) | Tribal Data
Umatilla Confederated Tribes (CTUIR)
Umatilla Confederated Tribes (CTUIR)
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | RAPID LIGHTNING (Ginter #2) IDFG | ALFD-WL-29 | ID | Pend Oreille | Bonner |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 |  | 932145 | 2008 | 2007-11-08
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | RAPID LIGHTNING-Lower Pack River (Ginter #1) IDFG | ALFD-WL-30 | ID | Pend Oreille | Bonner |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 |  | 992212 | 2007 | 2007-04-09 | 2007-04-09 | 2007-04-09 | 2007-04-02 | 2007-04-09 | 2007-04-03 | 2007-04-09
Oregon Department of Fish and Wildlife | Rattlesnake 3 | WILWF-WL-23 | OR | Willamette | Lane | Q3 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 172.5 | New Easement | 44.5129, -114.173 | 344000 | 346166 | 2015 | 2015-05-08 | [5 empty] | 2014-05-29
Oregon Department of Fish and Wildlife | Rattlesnake Butte (WILMIT-WL-26) | WILMIT-WL-26 | OR | Willamette | Lane |  | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , |  | Fee Title | 44.5129, -114.173 | 56000 | 54305 | 2012 | 2012-08-31 |  |  | 2012-08-29 | 2012-02-29 | 2012-05-10 | 2011-11-23 | [9 empty] | 51.00
Colville Confederated Tribes | Tribal Data
Salish and Kootenai Confederated Tribes
Oregon Department of Fish and Wildlife | Red Hills | WILWF-WL-18 | OR | Willamette | Yamhill | Q1 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 279.0 | New Easement | 44.5129, -114.173 | 2756000 | 3632833 | 2015 | 2014-12-29 |  |  |  |  | 2014-05-05 | 2014-02-13
Colville Confederated Tribes | Tribal Data
Colville Confederated Tribes
Colville Confederated Tribes
Salish and Kootenai Confederated Tribes
Colville Confederated Tribes
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Colville Confederated Tribes
Idaho Department of Fish and Game (IDFG) | Rudeen Ranch (SBT) | SIDHO-WL-2 |  |  |  | Q1 | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Exp | Sandra Fife | , |  | Mix | 44.5129, -114.173 |  | 1700000 | 2001 | 2000-12-21
Idaho Department of Fish and Game (IDFG) | Rudeen Ranch Land Acquistion | SIDHO-WL-2 | ID | Snake Upper | Power |  | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , | 2450.0 | Fee Title | 44.5129, -114.173 |  | 1700000 | 2001 | 2000-11-22
Salish and Kootenai Confederated Tribes | Tribal Data
Salish and Kootenai Confederated Tribes
Colville Confederated Tribes
Idaho Department of Fish and Game (IDFG) | Sandy Point (IDFG) | SIDHO-WL-16 | ID | Boise | Ada |  | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , |  | New Easement | 44.5129, -114.173 | 460000 | 460819 | 2012 | 2012-09-26
Oregon Department of Fish and Wildlife | Santiam-Kinston Hills | WILWF-WL-47 | OR | Willamette | Linn | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 406.0 | New Easement | 44.5129, -114.173 | 2300000 | 2571979 | 2018 | 2018-09-24
Yakama Confederated Tribes | Tribal Data
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Colville Confederated Tribes
Idaho Department of Fish and Game (IDFG) | Smith (Boise River) (IDFG) | SIDHO-WL-6 | ID | Boise | Ada | Q4 | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , |  | New Easement | 44.5129, -114.173 | 550000 | 359089 | 2008 | 2008-09-25
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Smith Creek (Sullivan) IDFG | ALFD-WL-36 | ID | Kootenai | Boundary |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 | 318000 | 319000 | 2008 | 2008-07-24 | 2008-07-28 | 2008-07-28 | 2008-07-23 | 2008-05-21 | 2008-07-23 | 2008-05-01
Oregon Department of Fish and Wildlife | Sorenson | WILMIT-WL-1 | OR | Willamette | Lane | Q4 | COMPLETED | 1992-068-00 | Willamette Basin Mitigation | Cap | Dorothy Welch | , |  | Fee Title | 44.5129, -114.173 |  | 162278 | 1998 | 1998-08-30
Oregon Department of Fish and Wildlife | South Yamhill River Floodplain Project | WILWF-WL-15 | OR | Willamette | Yamhill | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 91.2 | New Easement | 44.5129, -114.173 | 418400 | 420361 | 2013 | 2013-09-26 |  |  | 2013-09-20 | 2013-09-02 | 2013-07-01 | 2013-03-06
Umatilla Confederated Tribes (CTUIR) | Tribal Data
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | ST. JOE River (Sullivan) CdA | ALFD-WL-31 | ID | Coeur D'Alene | Benewah |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 | 1420000 | 1420816 | 2007 | 2007-09-20 | 2007-09-26 | 2007-09-26 | 2007-09-06 | 2007-09-11 | 2007-08-06 | 2007-09-26
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | ST. JOE River (Hepton) CdA | ALFD-WL-32 | ID | Coeur D'Alene | Benewah |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  |  | 44.5129, -114.173 | 17000 | 17000 | 2007 | 2007-09-20 | 2007-09-14 | 2007-09-14 | 2007-09-24 | 2007-09-14 | 2007-09-14 | 2007-09-14
US Fish and Wildlife Service (USFWS) | Steigerwald Lake NWR | STIGR-WL | WA | Columbia Lower | Clark |  |  | 1993-058-00 | Wa Coalition Mitigation Agreem | Exp | Joe Deherrera | , |  | Fee Title | 44.5129, -114.173 |  | 852852 | 1994 | 1994-09-06
Lower Columbia Estuary Partnership | Steigerwald Mobile Home Park |  | WA | Columbia Lower | Clark | Q2 | COMPLETED | 2003-011-00 | Columbia River Estuary Habitat Restoration | Exp | Anne Creason | , |  |  | 44.5129, -114.173 | 45700 | 500 | 2018 | 2018-02-13
Idaho Department of Fish and Game (IDFG) | Stewarship funding |  | ID | Snake Upper | Jerome |  | COMPLETED | 1995-057-00 | Southern Idaho Wildlife Mitigation | Cap | Sandra Fife | , |  |  | 44.5129, -114.173 | 14000000 | 14000000 | 2014 | 2014-09-26
Yakama Confederated Tribes | Tribal Data | [8 empty] | Exp | Michelle O'Malley | , |  | Fee Title | 44.5129, -114.173 | 100000 | 100996 | 2011 | 2011-09-01 | 2011-09-01 | 2011-09-01 | 2011-09-01 | 2011-09-01 | 2011-09-01 | 2011-09-01
Montana Fish, Wildlife and Parks (MFWP) | Swift-Lazy | HHDMT-WL-19 | MT | Flathead | Flathead | Q4 | COMPLETED | 2008-800-00 | Montana Resident Fish Habitat Aquisition | Cap | Cecilia Brown | , | 3180.0 | New Easement | 44.5129, -114.173 | 10600000 | 10733065 | 2018 | 2018-09-24
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Tacoma Creek - South (Carstens) KT | ALFD-WL-12 | WA | Pend Oreille | Pend Oreille |  | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 92.0 | Mix | 44.5129, -114.173 |  | 281263 | 2004 | 2004-06-04 |  |  |  | 2004-04-28 | 2004-06-01 | 2004-01-19
Yakama Confederated Tribes | Tribal Data
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Oregon Department of Fish and Wildlife | Thurston Hills 2 | WILWF-WF-22 | OR | Willamette | Lane | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 210.0 | New Easement | 44.5129, -114.173 | 940000 | 397910 | 2014 | 2014-09-26 | [5 empty] | 2014-06-19
Oregon Department of Fish and Wildlife | Thurston Hills Nature Park | WILWF-WL-16 | OR | Willamette | Lane | Q4 |  | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 106.0 | New Easement | 44.5129, -114.173 | 500000 | 500509 | 2013 | 2013-09-26 |  |  | 2013-09-20 | 2013-06-24 | 2013-09-04 | 2013-02-08
Salish and Kootenai Confederated Tribes | Tribal Data
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | TROUT CREEK (Stevens Lot) IDFG | ALFD-WL-34 | ID | Pend Oreille | Bonner |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 |  | 111415 | 2008 | 2008-02-14 |  |  | 2008-02-11 |  |  | 2007-12-05
Kootenai Tribe | Tribal Data
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Trout Creek Peninsula-Wheeler (KToI) | ALFD-WL-3 | ID | Kootenai | Boundary | Q3 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Exp | Virgil Watts III | , |  | New Easement | 44.5129, -114.173 |  | 155240 | 2002 | 2002-04-04
US Fish and Wildlife Service (USFWS) | Tualatin River National Wildlife Additions - Olesen #1 | TUALT-FF-1 |  |  |  | Q3 | COMPLETED | 2000-016-00 | Tualatin River National Wildlife Refuge Additions | Exp | Siena Lopez-Johnston | , |  |  | 44.5129, -114.173 |  | 577908 | 2002 | 2002-06-26
US Fish and Wildlife Service (USFWS) | Tualatin River National Wildlife Additions - Olesen #2 | TUALT-FF-2 |  |  |  | Q2 | COMPLETED | 2000-016-00 | Tualatin River National Wildlife Refuge Additions | Exp | Siena Lopez-Johnston | , |  |  | 44.5129, -114.173 |  | 859210 | 2001 | 2001-01-22
Colville Confederated Tribes | Tribal Data
Oregon Department of Fish and Wildlife | Turtle Flats | WILWF-WL-20 | OR | Willamette | Lane | Q4 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 60.2 | New Easement | 44.5129, -114.173 | 324000 | 325165 | 2015 | 2015-09-28 | [5 empty] | 2014-02-27
Yakama Confederated Tribes | Tribal Data
Yakama Confederated Tribes
Salish and Kootenai Confederated Tribes
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Upper Trimble Creek-Doramus (Kalispel Tribe) | KALTRIBE-WL-2 | WA | Pend Oreille | Pend Oreille |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Exp | Virgil Watts III | , |  | Fee Title | 44.5129, -114.173 |  | 305132 | 2000 | 2000-06-28
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Upper Trimble Creek-North (Testall) KT | ALFD-WL-9 | WA | Pend Oreille | Pend Oreille |  |  | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , | 241.0 | Mix | 44.5129, -114.173 |  | 277611 | 2004 | 2004-03-19 |  |  |  | 2004-03-10 | 2004-02-20 | 2003-12-30
Salish and Kootenai Confederated Tribes | Tribal Data
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Salish and Kootenai Confederated Tribes
Spokane Tribe
Spokane Tribe
Coeur D'Alene Tribe, Idaho Department of Fish and Game (IDFG), Kalispel Tribe, Kootenai Tribe | Westmond Lake (IDFG) | ALFD-WL-62 | ID | Pend Oreille | Bonner | Q1 | COMPLETED | 1992-061-00 | Albeni Falls Wildlife Mitigation Capital Land Acquisitions | Cap | Virgil Watts III | , |  |  | 44.5129, -114.173 |  | 118000 | 2000 | 1999-11-02
Nature Conservancy | Willow Creek #3/Cuddleback (TNC/ODFW) | AMAZN-WL-3 | OR | Willamette | Lane | Q4 | COMPLETED | 1992-059-00 | Amazon Basin/West Eugene Wetlands | Cap | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 |  |  | 2004 | 2004-09-29
Lower Columbia Estuary Partnership | Willow Grove (CLT) | WILGR-WL-1 | WA | Elochoman | Cowlitz |  | COMPLETED | 2003-011-00 | Columbia River Estuary Habitat Restoration | Exp | Anne Creason | , |  | New Easement | 44.5129, -114.173 | 200000 | 67130 | 2008 | 2008-08-26 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30 | 2008-09-30
Coeur D'Alene Tribe | Tribal Data | [8 empty] | Exp | Virgil Watts III | , | 147.6 | Fee Title | 44.5129, -114.173 |  | 325191 | 2002 | 2002-07-12 |  |  | 2002-05-17 | 2002-02-08 | 2002-06-10 | 2002-03-25
Oregon Department of Fish and Wildlife | Yamhela Oak Conservation Overlook | WILWF-WL-32 | OR | Willamette | Yamhill | Q2 | COMPLETED | 2011-003-00 | Willamette Wildlife Fund (WWF) | Cap | Sandra Fife | , | 169.8 | New Easement | 44.5129, -114.173 | 1423000 | 1540500 | 2016 | 2016-03-30
Salish and Kootenai Confederated Tribes | Tribal Data
Salish and Kootenai Confederated Tribes
Oregon Department of Fish and Wildlife | Zena Property Conservation Easement (TPL/ODFW) | WILMIT-WL-7 | OR | Willamette | Polk |  |  | 1992-068-00 | Willamette Basin Mitigation | Cap | Dorothy Welch | , |  | New Easement | 44.5129, -114.173 | 6000000 | 5000000 | 2007 | 2007-09-21 | 2007-09-26 | 2007-09-26 | 2007-09-26 | 2007-09-26 | 2007-09-26 | 2007-09-26
Nature Conservancy | Zumwalt Prairie | ZUMW-WL-1 | OR | Imnaha | Wallowa |  | COMPLETED | 2001-043-00 | Acquire 27,000 Camp Cr Ranch | Cap | Joe Deherrera | , | 27000.0 | New Easement | 44.5129, -114.173 |  | 1959500 | 2003 | 2003-01-17