## Table Only
Committed Power Purchase Requirements under Load Following: Example Schedule |  |  |  |  | 2024-05-24
BP-31 Example Above-CHWM Load: 0 aMW
BP-33 Example Above-CHWM Load: FY33 = 5 aMW, FY34 = 7 aMW
BP-35 Example Above-CHWM Load: FY35 = 8 aMW, FY36 = 9 aMW |  |  | Color Key: |  |  |  | BP-31 | [23 empty] | BP-33
|  |  | WRAP Winter 2032/2033 season | WRAP Winter 2033/2034 season | WRAP Winter 2034/2035 season |  | FY 2031 | [11 empty] | FY 2032 | [11 empty] | FY 2033 | [11 empty] | FY 2034
|  |  | WRAP Summer 2033 season | WRAP Summer 2034 season | WRAP Summer 2035 season |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
[7 empty] | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4 | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4 | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4 | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4
Contractual Party | Action | Ex. aMW amount | Related Process | Info provided how far in advance? | No Later Than Date | FY | FY 2032 N: WRAP Winter 2031/2032 season (Nov – Mar); FY 2032 J: WRAP Summer 2032 season (June – Sept); FY 2033 N: WRAP Winter 2032/2033 season (Nov – Mar); FY 2033 J: WRAP Summer 2033 season (June – Sept); FY 2034 N: WRAP Winter 2033/2034 season (Nov – Mar); FY 2034 J: WRAP Summer 2034 season (June – Sept)
BPA/ Customer | BPA posts and customer makes an election for Above-CHWM Loads for BP-33 | N/A | BP-33 | 15 mo. before start of rate period | 2031-07-31 | FY 2031 | FY 2031 J: 2031-07-31
Customer | Send BPA QCC and joint accreditation for 5 aMW Forward Showing information | 5 aMW | WRAP Winter 2032/2033 season | 1 YEAR in adv. of WRAP op. period | 2031-11-01 | FY 2032 | FY 2032 N: 2031-11-01
Customer | Send BPA QCC and joint accreditation 5 aMW Forward Showing information | 5 aMW | WRAP Summer 2033 season | 1 YEAR in adv. of WRAP op. period | 2032-06-01 | FY 2032 | FY 2032 J: 2032-06-01
Customer | Start scheduling 5 aMW Committed Power Purchase obligation | 5 aMW | FY 2033 | N/A | 2032-10-01 | FY 2033 | FY 2033 O: 2032-10-01
Customer | Send BPA QCC and joint accreditation 7 aMW Forward Showing | 7 aMW | WRAP Winter 2033/2034 season | 1 YEAR in adv. of WRAP op. period | 2032-11-01 | FY 2033 | FY 2033 O: 2032-11-01
Customer | Provide BPA a forecast of 5 aMW of physical resource(s) gen. schedule | 5 aMW | WRAP Winter 2032/2033 season | 1 MONTH in adv. of WRAP op. period | 2032-10-01 | FY 2033 | bar: FY 2033 O
Customer | Submit Day-Ahead physical resource schedule(s) | N/A | WRAP Winter 2032/2033 season | 1 DAY in adv. of WRAP op. period | 2032-10-31 | FY 2033 | FY 2033 O: 2032-10-01
Customer | Send BPA QCC and joint accreditation 7aMW Forward Showing information | 7 aMW | WRAP Summer 2034 season | 1 YEAR in adv. of WRAP op. period | 2033-06-01 | FY 2033 | FY 2033 M: 2033-06-01
Customer | Provide BPA a forecast of 5 aMW of physical resource(s) gen. schedule | 5 aMW | WRAP Summer 2033 season | 1 MONTH in adv. of WRAP op. period | 2033-05-01 | FY 2033 | FY 2033 M: 2033-05-01
Customer | Submit Day-Ahead physical resource schedule(s) | 5 aMW | WRAP Summer 2033 season | 1 DAY in adv. of WRAP op. period | 2033-05-31 | FY 2033 | bar: FY 2033 M
BPA/ Customer | BPA posts and customer makes an election for Above-CHWM Loads for BP-35 | N/A | BP-35 | 15 mo. before start of rate period | 2033-07-31 | FY 2033 | FY 2033 J: 2033-07-31
Customer | Start scheduling 7 aMW Committed Power Purchase obligation | 7 aMW | FY 2034 | N/A | 2033-10-01 | FY 2034 | FY 2034 O: 2033-10-01
Customer | Send BPA QCC and joint accreditation 8 aMW Forward Showing information | 8 aMW | WRAP Winter 2034/2035 season | 1 YEAR in adv. of WRAP op. period | 2033-11-01 | FY 2034 | bar: FY 2034 N
Customer | Provide BPA a forecast of 7 aMW of physical resource(s) generation schedule | 7 aMW | WRAP Winter 2033/2034 season | 1 MONTH in adv. of WRAP op. period | 2033-10-01 | FY 2034 | FY 2034 O: 2033-11-01
Customer | Submit Day-Ahead physical resource schedule(s) | 5 aMW | WRAP Winter 2033/2034 season | 1 DAY in adv. of WRAP op. period | 2033-10-31 | FY 2034 | FY 2034 O: 2033-10-01
Customer | Send BPA QCC and joint accreditation 8 aMW Forward Showing information | 8 aMW | WRAP Summer 2035 season | 1 YEAR in adv. of WRAP op. period | 2034-06-01 | FY 2034 | FY 2034 M: 2034-06-01
Customer | Provide BPA a forecast of 5 aMW of physical resource(s) generation schedule | 5 aMW | WRAP Summer 2034 season | 1 MONTH in adv. of WRAP op. period | 2034-05-01 | FY 2034 | FY 2034 M: 2034-05-01
Customer | Submit Day-Ahead physical resource schedule(s) | 5 aMW | WRAP Summer 2034 season | 1 DAY in adv. of WRAP op. period | 2034-05-31 | FY 2034

## Full Graphic
Committed Power Purchase Requirements under Load Following: Example Schedule |  |  |  |  | 2024-05-24
BP-31 Example Above-CHWM Load: 0 aMW
BP-33 Example Above-CHWM Load: FY33 = 5 aMW, FY34 = 7 aMW
BP-35 Example Above-CHWM Load: FY35 = 8 aMW, FY36 = 9 aMW |  |  | Color Key: |  |  |  | BP-31 | [23 empty] | BP-33
|  |  | WRAP Winter 2032/2033 season | WRAP Winter 2033/2034 season | WRAP Winter 2034/2035 season |  | FY 2031 | [11 empty] | FY 2032 | [11 empty] | FY 2033 | [11 empty] | FY 2034
|  |  | WRAP Summer 2033 season | WRAP Summer 2034 season | WRAP Summer 2035 season |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
[7 empty] | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4 | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4 | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4 | Q1 | Q1 | Q1 | Q2 | Q2 | Q2 | Q3 | Q3 | Q3 | Q4 | Q4 | Q4
Contractual Party | Action | Ex. aMW amount | Related Process | Info provided how far in advance? | No Later Than Date | FY | FY 2032 N: WRAP Winter 2031/2032 season (Nov – Mar); FY 2032 J: WRAP Summer 2032 season (June – Sept); FY 2033 N: WRAP Winter 2032/2033 season (Nov – Mar); FY 2033 J: WRAP Summer 2033 season (June – Sept); FY 2034 N: WRAP Winter 2033/2034 season (Nov – Mar); FY 2034 J: WRAP Summer 2034 season (June – Sept)
BPA/ Customer | BPA posts and customer makes an election for Above-CHWM Loads for BP-33 | N/A | BP-33 | 15 mo. before start of rate period | 2031-07-31 | FY 2031 | FY 2031 J: 2031-07-31
Customer | Send BPA QCC and joint accreditation for 5 aMW Forward Showing information | 5 aMW | WRAP Winter 2032/2033 season | 1 YEAR in adv. of WRAP op. period | 2031-11-01 | FY 2032 | FY 2032 N: 2031-11-01
Customer | Send BPA QCC and joint accreditation 5 aMW Forward Showing information | 5 aMW | WRAP Summer 2033 season | 1 YEAR in adv. of WRAP op. period | 2032-06-01 | FY 2032 | FY 2032 J: 2032-06-01
Customer | Start scheduling 5 aMW Committed Power Purchase obligation | 5 aMW | FY 2033 | N/A | 2032-10-01 | FY 2033 | FY 2033 O: 2032-10-01
Customer | Send BPA QCC and joint accreditation 7 aMW Forward Showing | 7 aMW | WRAP Winter 2033/2034 season | 1 YEAR in adv. of WRAP op. period | 2032-11-01 | FY 2033 | FY 2033 N: 2032-11-01
Customer | Provide BPA a forecast of 5 aMW of physical resource(s) gen. schedule | 5 aMW | WRAP Winter 2032/2033 season | 1 MONTH in adv. of WRAP op. period | 2032-10-01 | FY 2033 | FY 2033 O: 2032-10-01
Customer | Submit Day-Ahead physical resource schedule(s) | 5 aMW | WRAP Winter 2032/2033 season | 1 DAY in adv. of WRAP op. period | 2032-10-31 | FY 2033 | FY 2033 O: 2032-10-31
Customer | Send BPA QCC and joint accreditation 7aMW Forward Showing information | 7 aMW | WRAP Summer 2034 season | 1 YEAR in adv. of WRAP op. period | 2033-06-01 | FY 2033 | FY 2033 J: 2033-06-01
Customer | Provide BPA a forecast of 5 aMW of physical resource(s) gen. schedule | 5 aMW | WRAP Summer 2033 season | 1 MONTH in adv. of WRAP op. period | 2033-05-01 | FY 2033 | FY 2033 M: 2033-05-01
Customer | Submit Day-Ahead physical resource schedule(s) | 5 aMW | WRAP Summer 2033 season | 1 DAY in adv. of WRAP op. period | 2033-05-31 | FY 2033 | FY 2033 M: 2033-05-31
BPA/ Customer | BPA posts and customer makes an election for Above-CHWM Loads for BP-35 | N/A | BP-35 | 15 mo. before start of rate period | 2033-07-31 | FY 2033 | FY 2033 J: 2033-07-31
Customer | Start scheduling 7 aMW Committed Power Purchase obligation | 7 aMW | FY 2034 | N/A | 2033-10-01 | FY 2034 | FY 2034 O: 2033-10-01
Customer | Send BPA QCC and joint accreditation 8 aMW Forward Showing information | 8 aMW | WRAP Winter 2034/2035 season | 1 YEAR in adv. of WRAP op. period | 2033-11-01 | FY 2034 | FY 2034 N: 2033-11-01
Customer | Provide BPA a forecast of 7 aMW of physical resource(s) generation schedule | 7 aMW | WRAP Winter 2033/2034 season | 1 MONTH in adv. of WRAP op. period | 2033-10-01 | FY 2034 | FY 2034 O: 2033-10-01
Customer | Submit Day-Ahead physical resource schedule(s) | 7 aMW | WRAP Winter 2033/2034 season | 1 DAY in adv. of WRAP op. period | 2033-10-31 | FY 2034 | FY 2034 O: 2033-10-31
Customer | Send BPA QCC and joint accreditation 8 aMW Forward Showing information | 8 aMW | WRAP Summer 2035 season | 1 YEAR in adv. of WRAP op. period | 2034-06-01 | FY 2034 | FY 2034 J: 2034-06-01
Customer | Provide BPA a forecast of 5 aMW of physical resource(s) generation schedule | 5 aMW | WRAP Summer 2034 season | 1 MONTH in adv. of WRAP op. period | 2034-05-01 | FY 2034 | FY 2034 M: 2034-05-01
Customer | Submit Day-Ahead physical resource schedule(s) | 5 aMW | WRAP Summer 2034 season | 1 DAY in adv. of WRAP op. period | 2034-05-31 | FY 2034 | FY 2034 M: 2034-05-31