## Request List
Request# | CAISO# | Start | End | Main Element Impacted | Elements Involved | Path Affected
23-04125 | 13016840 | 01/28/2023 17:00 | 09/30/2026 23:59 | ROCKY REACH-MAPLE VALLEY NO 1 345kV LINE OPERATING AT 230KV | ROCKY REACH: 345/230KV TRANSFORMER 1, ROCKY REACH-MAPLE VALLEY NO 1 345kV LINE OPERATING AT 230KV, MAPLE VALLEY: 345/230KV TRANSFORMER 1 | WOCN, SOC/NOEL, CI, GEN, IROL, NOEL, NOH, SOC
23-08577 | 13856830 | 04/30/2023 18:57 | 01/01/2027 23:59 | VALHALLA: PCB B-280 | VALHALLA: PCB B-280
23-18445 | 14853282 | 12/14/2023 06:40 | 03/31/2025 16:00 | BCH - CHAPMAN: 5CX1 | BCH - CHAPMAN: 5CX1 | NI
24-09008 | 15780159 | 05/06/2024 18:00 | 05/15/2025 15:00 | ROCK CREEK: 230KV CAP GROUP 1 SECTION 1 INCLUDING PCB A-1719
24-17059 | 16817941 | 10/25/2024 01:00 | 06/30/2025 16:00 | WAUTOMA: SCHULTZ 1 500KV LINE SERIES CAP GROUP NO 1 |  | NOH, WOCN
24-17312 | 16800775 | 11/01/2024 00:01 | 03/31/2025 23:59 | LADWP - SYLMAR: PDCI SOUTH-NORTH LIMITATION |  | PDCI
25-00706 | 16841248 | 01/07/2025 20:00 | 03/25/2025 15:00 | OLYMPIA-SATSOP NO 2 230KV LINE INCLUDING PCB A-222 | OLYMPIA-SATSOP NO 2 230KV LINE, OLYMPIA: PCB A-222 | LOAD, SI, RP, NOEL, SOC, WOCN
25-00710 | 16840870 | 01/08/2025 06:00 | 04/29/2025 16:00 | OLYMPIA: PCB A-216 |  | NOEL, RP, SOC, WOCN
25-00794 |  | 01/27/2025 08:00 | 03/28/2025 15:00 | BENTON-RINGOLD SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE | CONNELL-SCOOTENEY SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE | TCLA
25-00203 | 16814062 | 01/27/2025 08:00 | 04/21/2025 15:00 | DRISCOLL-KNAPPA SECTION OF DRISCOLL-ASTORIA NO 1 115KV LINE | DRISCOLL: PCB B-2061, DRISCOLL: PCB B-2067
25-02339 |  | 02/01/2025 05:00 | 03/15/2025 19:00 | LADWP- VICTORVILLE-CENTURY 2 287KV LINE |  | PDCI
25-01945 |  | 02/03/2025 07:00 | 05/30/2025 17:00 | IPC- MIDPOINT - HEMINGWAY 500 KV line |  | ID-NW, NWACI
25-00431 | 16923560 | 02/10/2025 07:00 | 04/03/2025 15:00 | -USBR- HUNGRY HORSE: PCBS 2182 AND 2382 | HUNGRY HORSE PH: PCB 2182, HUNGRY HORSE PH: PCB 2382 | WOH, FLAT
25-02207 | 17164801 | 02/13/2025 08:00 | 03/14/2025 15:00 | ROSS: 230KV CAP GROUP 2 SECTION 3 INCLUDING LBD A-27 | ROSS: LBD A-27, ROSS: 230KV CAP GROUP 2 SECTION 3 | SOA, NOPE
25-00229 | 17035225 | 02/17/2025 08:00 | 03/28/2025 15:00 | RUPPERT ROAD-HORN RAPIDS SECTION OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE
25-01061 | 17069515 | 02/17/2025 18:00 | 03/24/2025 08:00 | ST JOHNS: 115KV WEST MAIN BUS INCLUDING THE B-50 MAIN BUS SECTIONALIZING DISC, 115KV WEST AUX BUS, PCB'S B-44 AND B-48, THE 230/115KV TRANSFORMER 1 INCLUDING THE ROSS-ST JOHNS NO 1 230KV LINE, AND THE ST JOHNS-PACW ST JOHNS NO 1 115KV LINE | ST JOHNS-PACW ST JOHNS NO 1 115KV LINE, ST JOHNS: 115KV WEST MAIN BUS, ST JOHNS: 115KV AUX BUS, ST JOHNS: PCB B-44, ST JOHNS: PCB B-48, ST. JOHNS: 230/115KV TRANSFORMER 1, ROSS-ST JOHNS NO 1 230KV LINE, ST JOHNS: B-50 MAIN BUS SECTIONALIZING DISC | LOAD, SOA, NOPE
25-02383 | 17181943 | 02/17/2025 19:00 | 03/07/2025 05:00 | PEARL: A-1165 TERMINAL OF MCLOUGHLIN-SHERWOOD NO 1 230KV LINE | PEARL: PCB A-1165, PEARL-SHERWOOD SECTION OF MCLOUGHLIN-SHERWOOD NO 1 230KV LINE | SOA, NOPE
25-00041 | 11095420 | 02/23/2025 03:00 | 03/27/2025 17:00 | -USBR- GRAND COULEE: PCB 5382 | -USBR- GRAND COULEE: PCB 5382 | NOH, WOCN, COI, NWACI, PDCI
25-00087 |  | 02/24/2025 18:00 | 08/20/2025 16:30 | PONDEROSA: 230KV NON-GIS NORTH BUS FROM REMOVED BUS SECTION EAST OF A-1811 DISC TO REMOVED JUMPERS FROM PCB A-1844 BUSHINGS TO A-1840 DISCONNECT INCLUDING A-1840 DISCONNECT
25-02413 |  | 02/24/2025 19:00 | 03/01/2025 05:00 | PGE- MCLOUGHLIN-PEARL-SHERWOOD 230KV LINE | MCLOUGHLIN-SHERWOOD NO 1 230KV LINE | SOA, WOCS, NOPE
25-00120 | 15576631 | 02/27/2025 08:00 | 04/24/2025 08:00 | JOHN DAY: MOD 4169 | JOHN DAY: PCB 4170 | NWACI, WOCS, WOJD, PDCI
25-01468 | 17048400 | 03/02/2025 22:00 | 03/06/2025 17:00 | GRAND COULEE: PCB 1172 INCLUDING 115KV AUX BUS SECTION 1 | GRAND COULEE: 115KV AUX BUS SECTION 1, GRAND COULEE: PCB 1172
25-00328 | 16878449 | 03/03/2025 06:00 | 03/03/2025 15:00 | WESTSIDE AVA-BELL NO 1 230KV LINE INCLUDING BELL: 230KV AUX BUS SECTION 1 AND PCB A-362 | WESTSIDE AVA-BELL NO 1 230KV LINE, BELL: 230KV AUX BUS SECTION 1, BELL: PCB A-362 | WOH, MT-NW
25-00773 |  | 03/03/2025 06:00 | 03/14/2025 17:00 | LIBBY PH-LIBBY NO 1 230KV LINE | MWTT CKT 7239 | GEN, FCRPS
24-11113 | 16072887 | 03/03/2025 07:00 | 03/14/2025 16:00 | CUSTER: 4268 BFR | CUSTER: PCB 4268 | BCHT, BCHW, NOEL, SOC, NI
25-02242 |  | 03/03/2025 07:00 | 05/04/2025 18:00 | SCL-BOTHELL: PCB 240-72
25-00779 | 16798463 | 03/03/2025 07:00 | 03/03/2025 16:00 | RAVER: PCB 4293 |  | NOEL, RP, SOC, WOCN
25-00561 | 16593320 | 03/03/2025 07:30 | 03/03/2025 16:00 | SLATT: 500/230KV TRANSFORMER 1 INCLUDING PCB'S A-1794, A-1791, A-1788 AND THE SHEPHERDS FLAT-SLATT 2 230KV LINE | SLATT: PCB A-1791, SLATT: PCB A-1794, SLATT: 500/230KV TRANSFORMER 1, SLATT: PCB A-1788, SHEPHERDS FLAT-SLATT NO 2 230KV LINE, MONTAGUE-SLATT TIE NO 1 230KV LINE, SLATT: 230KV CAP GROUP 2 SECTION 1, SLATT: 230KV CAP GROUP 2 SECTION 2, SHEPHERDS FLAT-SLATT NO 1 230KV LINE | WOJD, NWACI, GEN
25-00564 | 16593346 | 03/03/2025 07:30 | 03/03/2025 16:00 | SHEPHERDS FLAT-SLATT NO 1 230KV LINE INCLUDING SLATT: PCB'S A-1785 AND A-1797 | SLATT: PCB A-1797, SLATT: PCB A-1785, SHEPHERDS FLAT-SLATT NO 1 230KV LINE | JDAY, WOS, NWACI, WOJD
25-00576 | 16711060 | 03/03/2025 08:00 | 03/05/2025 16:00 | PAUL: 500KV PCB 4808 INCLUDING 500KV REACTOR 1 | PAUL: PCB 4808, PAUL: 500KV REACTOR 1
25-00796 | 16877279 | 03/03/2025 08:00 | 03/03/2025 15:00 | NASELLE: 115KV AUX BUS INCLUDING THE B-1711 AUX BUS DISCONNECT AND THE NASELLE-TARLETT #1 115KV LINE | NASELLE-TARLETT NO 1 115KV LINE, NASELLE: 115KV AUX BUS, NASELLE: PCB B-1711
25-00784 |  | 03/03/2025 08:00 | 03/31/2025 15:00 | COSMOPOLIS: PCB B-1335 INCLUDING ALL ASSOCIATED WIRING, RELAYS, FUSES, & ACB'S | COSMOPOLIS: PCB B-1335 | LOAD
25-00330 | 16287463 | 03/03/2025 08:00 | 03/19/2025 16:00 | CAPTAIN JACK: 4974/4975 TERMINAL OF CAPTAIN JACK-OLINDA 500KV LINE | CAPTAIN JACK-OLINDA NO 1 500KV LINE, CAPTAIN JACK: OLINDA 1 500KV LINE SERIES CAP GROUP 1, CAPTAIN JACK: PCB 4971, CAPTAIN JACK: PCB 4972 | BCHT, BCHW, COI, NI, NWACI
25-00264 | 16376261 | 03/03/2025 08:00 | 03/06/2025 15:00 | MALIN: PCB 4064 |  | NWACI, COI
25-00166 |  | 03/03/2025 08:00 | 03/18/2025 18:00 | SCL- EAST PINE 230KV BUS 1, BANK 96 AND SOUTH-EAST PINE 230KV LINE | EAST PINE (SCL)-SOUTH 230KV LINE | NOEL, SOC
25-00168 |  | 03/03/2025 08:00 | 03/18/2025 18:00 | SCL - EAST PINE-SOUTH 230KV LINE |  | SOC/NOEL
25-00783 | 16842572 | 03/03/2025 08:00 | 03/31/2025 15:00 | COSMOPOLIS: PCB B-1335 INCLUDING 115KV CAP GROUP #1 | COSMOPOLIS: 115KV CAP GROUP 1
25-02062 |  | 03/03/2025 09:00 | 03/07/2025 15:00 | UNITY: PCB B-1750 LINE RELAYS | UNITY: PCB B-1750, UNITY-PACIFIC SECTION OF UNITY-WEST BURLEY NO 1 138KV LINE
25-02055 | 17122860 | 03/03/2025 09:30 | 03/03/2025 10:00 | GRAND COULEE: PCB 1272 | GRAND COULEE-B212 SECTION OF GRAND COULEE-CRESTON NO 1 115KV LINE | OKLA
25-02056 | 17122884 | 03/03/2025 10:00 | 03/03/2025 10:30 | GRAND COULEE: PCB 1472 | GRAND COULEE-KELLER SECTION OF GRAND COULEE-OKANOGAN NO 2 115KV LINE | LOAD
25-02057 | 17120545 | 03/03/2025 10:30 | 03/03/2025 11:00 | GRAND COULEE: PCB 2472 | GRAND COULEE-NILLES CORNER SECTION OF GRAND COULEE-FOSTER CREEK NO 1 115KV LINE
25-02058 | 17122896 | 03/03/2025 11:00 | 03/03/2025 11:30 | GRAND COULEE: PCB 1572 | GRAND COULEE: 230/115KV BANK KX2A SWITCHYARD TIE | NOH, OKLA, LOAD
25-02415 |  | 03/03/2025 19:00 | 03/07/2025 05:00 | PGE- MCLOUGHLIN-PEARL-SHERWOOD 230KV LINE | MCLOUGHLIN-SHERWOOD NO 1 230KV LINE | SOA, WOCS, NOPE
24-02180 | 15526967 | 03/04/2025 08:00 | 03/04/2025 14:30 | KEELER: PCB A-859 INCLUDING 230KV REACTIVE GROUP 2 CAP SECTION 3 | KEELER: PCB A-859, KEELER: 230KV REACTIVE GROUP 2 CAP SECTION 3 | SOA, NOPE, WOCS
25-00876 | 16834114 | 03/04/2025 10:00 | 03/04/2025 10:15 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-00878 | 16834118 | 03/04/2025 14:15 | 03/04/2025 14:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-01620 | 17074461 | 03/05/2025 07:00 | 03/05/2025 08:00 | CENTRALIA SWITCHING STATION-TPWR COWLITZ SECTION OF CHEHALIS-COVINGTON NO 1 230KV LINE INCLUDING COWLITZ TAP | CENTRALIA SWITCHING STATION-TPWR COWLITZ SECTION OF CHEHALIS-COVINGTON NO 1 230KV LINE, COWLITZ TAP TO CHEHALIS-COVINGTON NO 1 230KV LINE | RP, NOEL, SOC, LOAD
25-01473 | 17074455 | 03/05/2025 07:00 | 03/05/2025 16:00 | TPWR COWLITZ-COVINGTON SECTION OF CHEHALIS-COVINGTON NO 1 230KV LINE INCLUDING COVINGTON PCB A-80 AND COVINGTON 230KV A/B SECTION 1 | TPWR COWLITZ-COVINGTON SECTION OF CHEHALIS-COVINGTON NO 1 230KV LINE, COVINGTON: 230KV AUX BUS SECTION 1 | RP, SOA, NOPE
25-00386 | 16361700 | 03/05/2025 07:00 | 03/06/2025 16:00 | PAUL: PCB 4536 |  | RP, WOCS, SOA, NOPE
24-00077 | 14975191 | 03/05/2025 08:00 | 03/05/2025 15:00 | KEELER: 500KV WEST BUS INCLUDING 500KV CAP GROUP 3 AND PCB'S 4322 AND 4763 | KEELER: PCB 4322, KEELER: PCB 4763, KEELER: 500KV WEST BUS, PEARL-KEELER NO 1 500KV LINE, KEELER: 500KV CAP GROUP 3 | SOA, NOPE, SIG, NWACI, WOCS
25-02022 | 17159916 | 03/06/2025 07:00 | 03/06/2025 15:00 | FAIRMOUNT: PCBS B-1378 & B-1384 | FAIRMOUNT: PCB B-1378, FAIRMOUNT: PCB B-1384
24-01095 | 15584846 | 03/06/2025 08:00 | 03/06/2025 16:00 | MCMINNVILLE: PCB B-382 | MCMINNVILLE: 115KV CAP GROUP 2
24-05075 | 17159877 | 03/06/2025 08:00 | 03/06/2025 15:00 | FAIRMOUNT: 230KV EAST BUS INCLUDING 230KV REACTOR 1, 230KV CAP GRP 3 AND 230KV PCBS A-1632, A-1634, A-1627, A-1622 AND A-1613 | FAIRMOUNT: 230/115KV TRANSFORMER 2, FAIRMOUNT: 230KV CAP GROUP 3, FAIRMOUNT: 230KV EAST MAIN BUS, FAIRMOUNT: 230KV REACTOR 1, FAIRMOUNT: PCB A-1632, FAIRMOUNT: PCB A-1634, FAIRMOUNT: PCB A-1627, FAIRMOUNT: PCB A-1622, FAIRMOUNT: PCB A-1613 | RP, LOAD
25-00683 | 16723622 | 03/06/2025 09:00 | 03/06/2025 15:00 | GRIZZLY-SUMMER LAKE NO 1-500KV LINE INCLUDING GRIZZLY PCB'S 5028/ 5025; PONDEROSA TAP TO THE GRIZZLY-SUMMER LAKE LINE, PONDEROSA 500/230KV TRANSFORMER 1 AND PCB 4618; SAND SPRINGS AND FORT ROCK 500KV SERIES CAP GROUPS 3; AND SUMMER LAKE PCB'S 4959/4958 | GRIZZLY-SUMMER LAKE NO 1 500KV LINE, GRIZZLY: PCB 5028, GRIZZLY: PCB 5025, GRIZZLY: PCB 4038, GRIZZLY: 500KV REACTOR 3, GRIZZLY-PONDEROSA SECTION OF GRIZZLY-SUMMER LAKE NO 1 500KV LINE, PONDEROSA TAP TO GRIZZLY-SUMMER LAKE NO 1 500KV LINE, PONDEROSA: PCB 4618, PONDEROSA: 500/230KV TRANSFORMER 1, PONDEROSA: PCB A-384, PONDEROSA: PCB A-398, PONDEROSA-SUMMER LAKE SECTION OF GRIZZLY-SUMMER LAKE NO 1 500KV LINE, SAND SPRINGS: GRIZZLY-SUMMER LAKE 1 500KV LINE SERIES CAP GROUP 3, FORT ROCK: GRIZZLY-SUMMER LAKE 1 500KV LINE SERIES CAP GROUP 3, SUMMER LAKE: PCB 4959, SUMMER LAKE: PCB 4958 | BCHT, BCHW, NI, NWACI, SIG, WOJD, COR, ID-NW
25-00271 |  | 03/09/2025 22:00 | 03/14/2025 17:00 | GRAND COULEE: PCB'S 2272 AND 2572 | GRAND COULEE: PCB 2272, GRAND COULEE: PCB 2572 | GEN, NOH
25-00047 | 15643304 | 03/10/2025 03:00 | 03/20/2025 17:00 | CHIEF JOSEPH: A-592 TERMINAL OF CHIEF JOSEPH PH-CHIEF JOSEPH 3 230KV LINE | CHIEF JOSEPH PH-CHIEF JOSEPH NO 3 230KV LINE | GEN, NOH, FCRPS
25-01765 |  | 03/10/2025 07:00 | 03/14/2025 14:00 | HEYBURN: 138KV MAIN BUS INCLUDING STATION SERVICE XFMR 1 | HEYBURN: 138KV MAIN BUS, UNITY-HEYBURN NO 1 138KV LINE, HEYBURN-HAY MILL SECTION OF HEYBURN-ADELAIDE NO 1 138KV LINE, HEYBURN: PCB B-1822, HEYBURN: PCB B-1812 | LOAD
25-01664 | 17082813 | 03/10/2025 07:00 | 03/14/2025 14:00 | RIVERTON-HEYBURN SECTION OF WEST BURLEY-HEYBURN NO 1 138KV LINE INCLUDING HEYBURN: 138KV AUX BUS AND PCB B-1793 | HEYBURN: PCB B-1794, HEYBURN: 138KV AUX BUS, HEYBURN: PCB B-1793, RIVERTON-HEYBURN SECTION OF WEST BURLEY-HEYBURN NO 1 138KV LINE
25-01594 | 17127196 | 03/10/2025 07:00 | 03/14/2025 14:00 | HEYBURN-MINICO SECTION OF IDAHO POWER HEYBURN-PAUL-ADELAIDE NO 1 138KV LINE INCLUDING HEYBURN: PCB B-1782 | HEYBURN: PCB B-1782
24-14161 | 16434016 | 03/10/2025 07:00 | 03/20/2025 15:00 | RAVER: 5OOKV CAP GROUP 1 SECTIONS 1, 2, 3 INCLUDING REACTIVE BUS AND PCB 4914 AND PCB 4921 | RAVER: PCB 4914, RAVER: PCB 4917, RAVER: PCB 4919, RAVER: PCB 4722, RAVER: PCB 4921, RAVER: 500KV CAP GROUP 1 SECTION 1, RAVER: 500KV CAP GROUP 1 SECTION 2, RAVER: 500KV CAP GROUP 1 SECTION 3 | NOEL, RP, SOC, IROL, WOCN
25-01946 | 17093531 | 03/10/2025 07:00 | 03/14/2025 14:00 | HEYBURN: B-1782 TERMINAL OF THE IDAHO POWER FEEDER 1 | HEYBURN: IDAHO POWER CO 138KV FEEDER 1, HEYBURN: PCB B-1782
25-01312 | 17003948 | 03/10/2025 08:00 | 03/17/2025 15:00 | JOHN DAY: PCB 4131 SEL BFR AND BREAKER DIFF | JOHN DAY: PCB 4131 | NWACI, WOJD, WOS, PDCI
24-03961 | 16537325 | 03/10/2025 08:00 | 03/13/2025 16:00 | FOREST GROVE: PCB B-1284
25-02073 | 17122219 | 03/10/2025 08:00 | 03/27/2025 14:00 | BIG EDDY: PCB 4209 SEL BFR | BIG EDDY: PCB 4209, BIG EDDY 500: KNIGHT LOR SET 1, BIG EDDY 500: BANK NO 5 LOR SET 1 | GEN, PDCI, WOJD, BGEDY, NWACI
25-00682 | 16856709 | 03/10/2025 08:00 | 03/13/2025 15:00 | MALIN: PCB 4072 |  | NWACI, COI
25-00510 | 16512144 | 03/10/2025 08:00 | 03/10/2025 15:00 | HANFORD: PCB 4083 |  | NOH, WOM, WOS
25-00347 | 16876891 | 03/11/2025 06:00 | 03/12/2025 16:00 | BELL: PCB A-378 | BELL: 230KV CAP GROUP 9 SECTION 1, BELL: 230KV CAP GROUP 9 SECTION 2, BELL: 230KV CAP GROUP 9 SECTION 3, BELL: PCB A-931, BELL: PCB A-932, BELL: PCB A-933 | MT-NW, WOH
24-08703 | 16225691 | 03/11/2025 08:00 | 03/11/2025 16:00 | WHITE BLUFFS: PCB B-1362 INCLUDING 115KV CAP GRP NO. 1 | WHITE BLUFFS: PCB B-1362, WHITE BLUFFS: 115KV CAP GROUP 1 | LOAD
25-00615 | 16689512 | 03/11/2025 10:00 | 03/11/2025 10:15 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | GEN, NOH, WOCN
25-00616 | 16689522 | 03/11/2025 14:15 | 03/11/2025 14:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | GEN, NOH, WOCN
25-00556 | 16936725 | 03/12/2025 08:00 | 03/12/2025 15:00 | ASHE: 230KV CAP GROUP 2 INCLUDING PCB A-892 | ASHE: PCB A-892, ASHE: 230KV CAP GROUP 2 | NOH, TCLA
25-00720 | 16770921 | 03/12/2025 08:00 | 03/13/2025 17:00 | GRIZZLY-CAPTAIN JACK NO 1 500KV LINE, INCLUDING PONDEROSA: PCB 4942 AND 500/230KV TRANSFORMER 2, SASP, FORT, AND SYCN: 500KV SERIES CAP GROUPS 1 | PONDEROSA: 500/230KV TRANSFORMER 2, SAND SPRINGS: GRIZZLY-CAPTAIN JACK 1 500KV LINE SERIES CAP GROUP 1, FORT ROCK: GRIZZLY-CAPTAIN JACK 1 500KV LINE SERIES CAP GROUP 1, SYCAN: GRIZZLY-CAPTAIN JACK 1 500KV LINE SERIES CAP GROUP 1, PONDEROSA TAP TO GRIZZLY-CAPTAIN JACK NO 1 500KV LINE | BCHT, BCHW, NI, NWACI, SIG, COR
25-02326 | 17177413 | 03/13/2025 08:00 | 03/13/2025 09:00 | NASELLE: PCB B-1711
25-02327 | 17181227 | 03/13/2025 09:00 | 03/13/2025 10:00 | NASELLE: PCB B-1715
25-02329 | 17181234 | 03/13/2025 10:00 | 03/13/2025 11:00 | NASELLE: PCB B-1717
25-02330 | 17181236 | 03/13/2025 11:00 | 03/13/2025 12:00 | NASELLE: PCB B-1716
25-02331 | 17181237 | 03/13/2025 12:00 | 03/13/2025 13:00 | NASELLE: PCB B-1721
24-11117 | 16072960 | 03/14/2025 16:00 | 03/14/2025 16:30 | CUSTER: PCB 4272 |  | BCHT, BCHW, NOEL, SOC, NI
25-00056 | 14839849 | 03/15/2025 08:00 | 03/16/2025 18:00 | RAS - DITTMER: RAS AC-A CONTROLLER, MUNRO: RAS AC-B CONTROLLER, RAS SYNCHROPHASOR-A CONTROLLER, RAS SYNCHROPHASOR-B CONTROLLER, MALIN FACRI A AND B | RAS - DITTMER: RAS AC-A CONTROLLER, MUNRO: RAS AC-B CONTROLLER, RAS SYNCHROPHASOR-A CONTROLLER, RAS SYNCHROPHASOR-B CONTROLLER, MALIN FACRI A AND B, MUNRO: RAS AC-B CONTROLLER, DITTMER: RAS AC-A CONTROLLER, DITTMER: RAS SYNCHROPHASOR-A CONTROLLER, MUNRO: RAS SYNCHROPHASOR-B CONTROLLER | SIG, COI, NOH, NWACI, PDCI, WOM, WOS, NI, WOJD, WOLM
25-00272 | 17003791 | 03/16/2025 22:00 | 03/21/2025 17:00 | GRAND COULEE: 230/115KV TRANSFORMER KX2A INCLUDING PCB'S 5182, 2372 AND THE 115KV AUX BUS SECT 2 | GRAND COULEE: PCB 5182, GRAND COULEE: PCB 2372, GRAND COULEE: 230/115KV BANK KX2A SWITCHYARD TIE | NOH, WOCN, OKLA, LOAD
25-00774 | 17115257 | 03/17/2025 06:00 | 03/28/2025 17:00 | LIBBY: LIBBY PH NO 2 MWTT CKT # 7238 | LIBBY PH-LIBBY NO 2 230KV LINE | GEN, FCRPS
25-01193 | 16999825 | 03/17/2025 06:00 | 03/18/2025 16:00 | BELL: 115KV MAIN BUS SECTIONS 2 & 3 INCLUDING PCB'S B-354, B-356, B-358, B-360, B-362, AND B-900 | BELL: 115KV MAIN BUS SECTION 2, BELL: 115KV MAIN BUS SECTION 3, BELL: PCB B-354, BELL: PCB B-356, BELL: PCB B-358, BELL: PCB B-360, BELL: PCB B-362, BELL: PCB B-900, BELL-AVA BEACON NO 1 115KV LINE, BELL-AVA NORTHEAST NO 3 115KV LINE, SPRINGHILL-BELL SECTION OF CRESTON-BELL NO 1 115KV LINE, BELL-BIGELOW SECTION OF BELL-TRENTWOOD NO 2 115KV LINE, BELL: PCB A-376, BELL: PCB A-372 | SOB, WOH, GEN, LOAD, MT-NW
25-00672 | 17086784 | 03/17/2025 07:00 | 03/17/2025 11:00 | INTALCO: PCB A-1016 BFR | INTALCO: PCB A-1016 | BCHT, BCHW
25-01126 | 16898481 | 03/17/2025 07:00 | 03/20/2025 16:00 | ROCKY REACH: 345/230 KV TRANSFORMER 1 | ROCKY REACH: 345/230KV TRANSFORMER 1 | SOC/NOEL, WOCN, NOH, IROL, GEN, NOEL, SOC
25-00323 | 16972001 | 03/17/2025 08:00 | 03/21/2025 15:00 | ALVEY: B-582 & B-584 TERMINALS OF THE SPRNGFLD UTIL BRD 115KV FEEDER 1 TO 10TH STREET | ALVEY: SPRNGFLD UTIL BRD 115KV FEEDER 1 TO 10TH STREET, ALVEY: PCB B-582, ALVEY: PCB B-584
25-00589 | 16971769 | 03/17/2025 08:00 | 03/21/2025 15:00 | ALVEY: 115KV AUX BUS | ALVEY: PCB B-586
25-00723 | 16807408 | 03/17/2025 08:00 | 03/27/2025 16:00 | PONDEROSA: 500/230KV TRANSFORMER 2, INCLUDING PCB 4942 | PONDEROSA: PCB 4942 | NWACI, COR
25-00131 | 15980354 | 03/17/2025 08:00 | 03/20/2025 14:30 | KEELER: PCB B-1078
25-00540 | 16711017 | 03/17/2025 08:00 | 03/17/2025 15:00 | PEARL: PCB 4283 |  | SOA, NOPE
25-01764 | 17086968 | 03/17/2025 11:00 | 03/17/2025 15:00 | INTALCO: PCB A-1020 BFR | INTALCO: PCB A-1020 | BCHT, BCHW
25-00675 | 17086641 | 03/18/2025 07:00 | 03/18/2025 15:00 | CUSTER-INTALCO NO 2 230KV LINE INCLUDING INTALCO PCB'S A-1016, A-1020 AND CUSTER PCB'S A-1250, A-1546 | INTALCO: PCB A-1016, INTALCO: PCB A-1020, CUSTER: PCB A-1250, CUSTER: PCB A-1546, CUSTER-INTALCO NO 2 230KV LINE | BCHT, BCHW, NOEL, SOC, NI, LOAD
25-00541 | 16711029 | 03/18/2025 08:00 | 03/20/2025 15:00 | PEARL: PCB 5452 |  | SOA, NOPE
25-00637 | 16690677 | 03/18/2025 08:00 | 03/18/2025 15:00 | ASHE: PCB 4909, INCLUDING 500KV REACTOR 2 | ASHE: 500KV REACTOR 2 | FCRPS, NOH, NWACI
25-00265 | 16999600 | 03/18/2025 08:00 | 03/20/2025 15:00 | HILLTOP: PCB A-1529 |  | RATS, NWACI
25-00898 | 16834121 | 03/18/2025 10:00 | 03/18/2025 10:15 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 |  | GEN, NOH, WOCN
25-00899 | 16834136 | 03/18/2025 14:15 | 03/18/2025 14:30 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 |  | GEN, NOH, WOCN
25-01196 | 17037252 | 03/19/2025 07:00 | 03/20/2025 16:00 | BELL: 115KV MAIN BUS SECTIONS 1 AND 2 INCLUDING PCB'S B-346, B-348, B-350, B-354 AND B-356 | BELL: 115KV MAIN BUS SECTION 1, BELL: 115KV MAIN BUS SECTION 2, BELL: PCB B-346, BELL: PCB B-348, BELL: PCB B-350, BELL: PCB B-354, BELL: PCB B-356, BELL: 115KV AUX BUS, BELL-AVA NORTHEAST NO 3 115KV LINE, BELL-MEAD SECTION OF BELL-ADDY NO 1 115KV LINE, SPRINGHILL-BELL SECTION OF CRESTON-BELL NO 1 115KV LINE | SOB, WOH, GEN, LOAD
25-01472 | 17067770 | 03/19/2025 07:00 | 03/19/2025 16:00 | COVINGTON-CRESTON SCL #1 230KV LINE INCLUDING COVINGTON PCB A-82 AND COVINGTON 230KV AUX BUS SECTION 1 | COVINGTON: 230KV AUX BUS SECTION 1, COVINGTON: PCB A-82, COVINGTON-CRESTON SCL NO 1 230KV LINE | NOEL, SOC
25-00638 | 16690695 | 03/19/2025 08:00 | 03/19/2025 16:00 | ASHE: 500KV NORTH BUS, INCLUDING PCB 4901 | ASHE: PCB 4940, ASHE: PCB 5466, ASHE: PCB 4888, ASHE: PCB 4901, ASHE: PCB 5327, ASHE: 500KV NORTH BUS | NWACI, WOCS, WOJD, WOM, FCRPS, WOS, GEN, NOH, WOLM
25-00190 | 16040961 | 03/19/2025 08:00 | 03/19/2025 12:00 | LOWER GRANITE: PCB 4770 |  | GEN, MT-NW, NOH, WOH, WOLM
25-00192 | 16506288 | 03/19/2025 08:00 | 03/19/2025 11:00 | HATWAI: PCB 4708 |  | MT-NW, NOH, WOH, WOLM
25-00193 | 16506294 | 03/19/2025 11:30 | 03/19/2025 14:30 | HATWAI: PCB 4710 |  | MT-NW, NOH, WOH, WOLM
25-00191 | 16041206 | 03/19/2025 12:00 | 03/19/2025 16:00 | LOWER GRANITE: PCB 4776 |  | MT-NW, WOH, WOLM, GEN
25-01474 | 17067877 | 03/20/2025 07:00 | 03/20/2025 16:00 | COVINGTON-DUWAMISH SCL NO 1 230KV LINE INCLUDING COVINGTON 230KV A/B SECTION 2 | COVINGTON-DUWAMISH NO 1 230KV LINE, COVINGTON: 230KV AUX BUS SECTION 2 | NOEL, SOC
25-00070 | 16771698 | 03/20/2025 08:00 | 04/17/2025 15:00 | MALIN-ROUND MOUNTAIN NO 1 500KV LINE INCLUDING THE PG&E ROUND MOUNTAIN 500KV SERIES CAP GROUP | MALIN-ROUND MOUNTAIN NO 1 500KV LINE, MALIN: PG&E ROUND MOUNTAIN 1 500KV LINE SERIES CAP GROUP | BCHT, BCHW, NI, COI
25-00274 | 17035441 | 03/23/2025 22:00 | 04/18/2025 17:00 | -USBR GRAND COULEE- 115/12KV TRANSFORMER KLN9A | GRAND COULEE: PCB 1072
25-00570 | 16593989 | 03/24/2025 07:00 | 03/24/2025 16:00 | MAPLE VALLEY-EAST PINE NO 1 230KV LINE, INCLUDING MAPLE VALLEY: PCB A-1116 AND 230KV AUX BUS SECT 1 | MAPLE VALLEY: PCB A-1116 | NOEL, SOC
25-00397 | 17080296 | 03/24/2025 07:30 | 03/25/2025 16:00 | CAPTAIN JACK: PCB 4996 |  | NWACI, COI
25-00579 | 16978031 | 03/24/2025 08:00 | 03/24/2025 18:00 | BIG EDDY: 230KV MAIN BUS SECTION 1 INCLUDING PCB'S A-696, A-800, A-802, A-804, A-806, A-848, A-812 AND A-826 | BIG EDDY: 230KV MAIN BUS SECTION 1, BIG EDDY: PCB A-696, BIG EDDY: PCB A-800, BIG EDDY: PCB A-802, BIG EDDY: PCB A-804, BIG EDDY: PCB A-806, BIG EDDY: PCB A-848, BIG EDDY: PCB A-812, BIG EDDY: 230/115KV TRANSFORMER 1, BIG EDDY: 500/230KV TRANSFORMER 2, BIG EDDY-QUENETT CREEK NO 2 230KV LINE, BIG EDDY-SPRING CREEK NO 1 230KV LINE, BIG EDDY-PARKDALE SECTION OF BIG EDDY-TROUTDALE NO 1 230KV LINE, THE DALLES PH-BIG EDDY NO 3 230KV LINE, BIG EDDY: PCB A-826, BIG EDDY: 230KV AUX BUS SECTION 1, FOSSIL-MUDDY RANCH SECTION OF FOSSIL-MAUPIN 69KV LINE | WOCS, BGEDY, COI, NWACI, PDCI, WOJD, GEN, SIG, FCRPS
25-00542 | 16711036 | 03/24/2025 08:00 | 03/27/2025 15:00 | PEARL: PCB 5455 |  | SOA, NOPE
24-15131 |  | 03/24/2025 08:00 | 03/28/2025 15:00 | NVE - HILLTOP-FORT SAGE 345KV LINE |  | RATS
25-00123 | 16957134 | 03/24/2025 08:00 | 04/03/2025 15:00 | KEELER: 230KV SVC INCLUDING PCB A-897 | KEELER: PCB A-897, KEELER: 20KV PCB L-1675, KEELER: 230/20KV TRANSFORMER 4, KEELER: 230KV SVC | SOA, NOPE, LOAD, WOCS
25-01062 | 17069477 | 03/24/2025 09:00 | 03/24/2025 18:00 | ST JOHNS: 115KV MAIN AND AUX BUSSES | ST. JOHNS: 230/115KV TRANSFORMER 1, ST. JOHNS: 115/57KV TRANSFORMER 5, ROSS-ST JOHNS NO 1 230KV LINE, ST JOHNS-KEELER NO 2 115KV LINE, ST JOHNS-PACW ST JOHNS NO 1 115KV LINE, ST JOHNS-ST HELENS NO 1 115KV LINE, ST JOHNS: PCB B-34, ST JOHNS: PCB B-40, ST JOHNS: PCB B-42, ST JOHNS: PCB B-44, ST JOHNS: PCB B-48, ST JOHNS: PCB B-80 | LOAD, SOA, NOPE
25-00338 | 16935785 | 03/24/2025 10:00 | 03/24/2025 15:00 | CRESTON: PCB B-437 | CRESTON-EGYPT SECTION OF CRESTON-BELL NO 1 115KV LINE
24-03651 | 15570812 | 03/25/2025 06:00 | 03/26/2025 20:00 | MAPLE VALLEY: 230KV M/B SECTION 1 INCLUDING PCBs A-1146, A-1106, A-1108, A-1114, A-1116, A-1118, A-1120, A-1124, A-1140 AND 230KV/240V M/B SECT 1 SS XFMR | MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 1, MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 2, MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 3, MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 4, MAPLE VALLEY-DUWAMISH NO 1 230KV LINE, COVINGTON-MAPLE VALLEY NO 2 230KV LINE, MAPLE VALLEY-EAST PINE NO 1 230KV LINE, ROCKY REACH-MAPLE VALLEY NO 1 345KV LINE, MAPLE VALLEY-TALBOT NO 1 230KV LINE, SNO-KING-MAPLE VALLEY NO 2 230KV LINE | NOEL, SOC, WOCN, NI, CI, IROL, NOH, SIG
25-01063 | 16896095 | 03/25/2025 07:00 | 03/26/2025 16:00 | ROCKY REACH-MAPLE VALLEY NO 1 345KV LINE, INCLUDING ROCKY REACH: 345/230KV TRANSFORMER 1 | ROCKY REACH: 345/230KV TRANSFORMER 1 | CI, IROL, NOEL, NOH, SOC, WOCN, GEN
24-07896 | 16241378 | 03/25/2025 07:30 | 03/25/2025 15:00 | KEELER: 230/115KV TRANSFORMER 1 INCLUDING 13.8KV TERTIARY BUS, L-1381 SVC FDR DISC, 1W FDR SIDE AND BYPASS DISCONNECTS | KEELER: 230/115KV TRANSFORMER 1, KEELER: PCB A-860, KEELER: PCB B-1066, KEELER: 13.8KV PCB 1W STATION SERVICE 1 | SOA, LOAD, NOPE
25-01081 |  | 03/25/2025 08:00 | 04/11/2025 15:00 | ST JOHNS: ROSS-ST JOHNS NO 1 230KV LINE INCLUDING 230/115KV TRANSFORMER BANK 1 , 115KV AUX BUS, PCB'S B-34 AND B-80 AND 115/57KV TRANSFORMER BANK NO 5 | ROSS-ST JOHNS NO 1 230KV LINE, ST. JOHNS: 230/115KV TRANSFORMER 1, ST JOHNS: 115KV AUX BUS, ST JOHNS: PCB B-34, ST JOHNS: PCB B-80, ST. JOHNS: 115/57KV TRANSFORMER 5, ST JOHNS: PACIFICORP (PACW) 57KV FEEDER 1 TO KNOTT, ST JOHNS: PCB B-48 | LOAD, SOA, NOPE
25-00617 | 16689607 | 03/25/2025 10:00 | 03/25/2025 10:15 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
25-00618 | 16689618 | 03/25/2025 14:15 | 03/25/2025 14:30 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
25-00752 | 17177011 | 03/26/2025 07:00 | 03/26/2025 19:00 | OLYMPIA: 230KV WEST MAIN INCLUDING PCB A-222, 230KV WEST AUX BUS AND OLYMPIA-SATSOP NO 2 230KV LINE | OLYMPIA-SATSOP NO 2 230KV LINE, OLYMPIA: PCB A-1770, OLYMPIA: 230KV WEST MAIN BUS, OLYMPIA: 230KV WEST AUX BUS, CHEHALIS-OLYMPIA NO 1 230KV LINE, OLYMPIA-SHELTON NO 4 230KV LINE, OLYMPIA: 230KV CAP GROUP 2 SECTION 2, OLYMPIA: 230KV CAP GROUP 2 SECTION 1, OLYMPIA: 230/115KV TRANSFORMER 1, OLYMPIA: PCB A-216, OLYMPIA: 230KV CENTER AUX BUS | LOAD, SI, RP, SOA, NOPE, NOEL, SOC, WOCN
25-01949 | 17094238 | 03/26/2025 08:00 | 03/26/2025 15:00 | CHIEF JOSEPH: PCB A-594 BFR | CHIEF JOSEPH: BRAKING RESISTOR, CHIEF JOSEPH: PCB A-594 | NOH, SIG, NWACI, WOCN
25-02075 | 17122244 | 03/27/2025 14:00 | 03/27/2025 15:00 | BIG EDDY: PCB 4860 |  | PDCI, WOJD, BGEDY, NWACI
24-15784 | 17041659 | 03/28/2025 06:00 | 03/28/2025 20:00 | OLYMPIA: 230KV EAST SECTION OF WEST MAIN BUS | OLYMPIA-SHELTON NO 4 230KV LINE, OLYMPIA: 230/115KV TRANSFORMER 2, OLYMPIA: 230KV CAP GROUP 2 SECTION 1, OLYMPIA: 230KV CAP GROUP 2 SECTION 2, OLYMPIA: PCB A-1773, OLYMPIA: PCB A-359, OLYMPIA: PCB A-208, OLYMPIA: PCB A-210, OLYMPIA: PCB A-212 | LOAD, PA, RP, SOA, NOPE, NOEL, SOC, WOCN
24-15803 | 17043401 | 03/28/2025 07:00 | 04/03/2025 16:00 | OLYMPIA: 230KV WEST MAIN BUS PT'S | OLYMPIA: 230KV EAST SECTION OF WEST MAIN BUS, OLYMPIA-SHELTON NO 4 230KV LINE, OLYMPIA: 230KV CAP GROUP 2 SECTION 1, OLYMPIA: 230KV CAP GROUP 2 SECTION 2, OLYMPIA: PCB A-208, OLYMPIA: PCB A-210, OLYMPIA: PCB A-212, OLYMPIA: 230/115KV TRANSFORMER 2, OLYMPIA: LBD A-223, OLYMPIA: LBD A-225 | LOAD, PA, RP, SOA, NOPE, NOEL, SOC, WOCN
25-00057 | 14839859 | 03/29/2025 08:00 | 03/30/2025 18:00 | RAS - DITTMER: RAS AC-A CONTROLLER, MUNRO: RAS AC-B CONTROLLER, RAS SYNCHROPHASOR-A CONTROLLER, RAS SYNCHROPHASOR-B CONTROLLER, MALIN FACRI A AND B | RAS - DITTMER: RAS AC-A CONTROLLER, MUNRO: RAS AC-B CONTROLLER, RAS SYNCHROPHASOR-A CONTROLLER, RAS SYNCHROPHASOR-B CONTROLLER, MALIN FACRI A AND B, MUNRO: RAS AC-B CONTROLLER, DITTMER: RAS AC-A CONTROLLER, DITTMER: RAS SYNCHROPHASOR-A CONTROLLER, MUNRO: RAS SYNCHROPHASOR-B CONTROLLER | SIG, COI, NOH, NWACI, PDCI, WOM, WOS, NI, WOJD, WOLM
25-00276 | 17037636 | 03/30/2025 22:00 | 04/11/2025 17:00 | GRAND COULEE: PCB 7182 |  | GEN, NOH, WOCN
25-00404 |  | 03/30/2025 22:00 | 04/11/2025 17:00 | GRAND COULEE: 7089 BSD, GRAND COULEE: 7387 DSC, GRAND COULEE: 7487 DSC, GRAND COULEE: 230KV AUX BUS SECTION 3, GRAND COULEE: 7081 MAIN BUS SECTIONALIZING DISC, GRAND COULEE: 7083 MAIN BUS SECTIONALIZING DISC, GRAND COULEE: 7181 LINE SIDE DISC, GRAND COULEE: 7183 MAIN BUS DISC, GRAND COULEE: 7189 AUX BUS DISC, GRAND COULEE: 7285 LINE SIDE DISC, GRAND COULEE: 7287 MAIN BUS DISC, GRAND COULEE: 7289 AUX BUS DISC, GRAND COULEE: 7389 AUX BUS DISC, GRAND COULEE: 7489 AUX BUS DISC, GRAND COULEE: 7889 AUX BUS DISC, GRAND COULEE: 8089 AUX BUS DISC, GRAND COULEE: PCB 7084, GRAND COULEE: PCB 7182, GRAND COULEE: PCB 7286, GRAND COULEE: PCB 7382 |  | GEN, NOH, WOCN, WOH
25-01488 | 17075233 | 03/31/2025 06:00 | 04/03/2025 15:00 | MINIDOKA PH: 138KV MAIN BUS |  | GEN
25-00976 | 16898377 | 03/31/2025 07:00 | 04/01/2025 16:00 | ASHE: 500KV REACTOR 1, INCLUDING PCB 4907 | ASHE: PCB 4907, ASHE: 500KV REACTOR 1 | FCRPS, NOH, NWACI
25-00266 | 17035415 | 03/31/2025 08:00 | 04/25/2025 15:00 | RUPPERT RD-HORN RAPIDS SECTION INCLUDING HORN RAPIDS TAP OF THE RED MOUNTAIN-WHITE BLUFFS #1 115KV LINE | HORN RAPIDS TAP TO RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE, RUPPERT ROAD-HORN RAPIDS SECTION OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE, HORN RAPIDS-WHITE BLUFFS SECTION OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE | TCLA, LOAD
25-00727 | 16807512 | 03/31/2025 08:00 | 04/17/2025 17:00 | PONDEROSA: 500/230KV TRANSFORMER 1, INCLUDING PCBs 4618, A-398 AND A-384 | PONDEROSA: PCB 4618 | NWACI, COR
25-01291 | 16997367 | 03/31/2025 08:00 | 03/31/2025 15:30 | CHIEF JOSEPH: PCB 4730 |  | NOEL, NOH, SOC, WOCN, NWACI